LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boola Boola-2 | REPORT No. : | 30 | DFS: | 29 | DATE : | 30-06-07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1887.00m | LAST DEPTH : | 1887.00m | 24 HR PROGRESS: | 0 | PTD : | 2000 |
| TOTAL FUEL : | 23250 | FUEL USAGE : | 4010 | DAYCOST : $ | 51,251 | CUM. COST : $ | 2,624,458 |
| 0600 OPS : | 0-0 – locate free point in drill collars – prepare for back off shot |
| Next 24 Hrs Op | Wiper trip – Well logging |
| Site Personnel: | Dave Hair - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 8 | 9 |  | Drilling |  |  | Density | 1.279 | S.G. |
| Size (mm) | 216 | 216 |  | Tripping – Jarring pipe | 17 |  | Viscosity | 42 | Sec |
| Make | Reed | Reed |  | Wireline / fishing | 7 |  | Water Loss | 13.5 | Cc |
| Type | TD43AP | TD53 AP |  | Rigged up BOP |  |  | pH | 8 | Strip |
| IADC Code | 4-3-7 | 5-3-7 |  | Slip cut Line |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | EM2047 | WC6626 |  | Circulate Sample |  |  | PV / YP | 12/20 | Cp/lb/100’ |
| Nozzles (32) | 12-12-12 | 12-12-13 |  | Casing |  |  | Gels | 13/20 | S/m |
| Depth in (m) | 1594 | 1821 |  | F.I.T |  |  | Sand | tr | % Vol |
| Depth out (m) | 1821 | inc |  | Surveys |  |  | Solids | 12.5 | % Vol |
| Total Metres | 227 | 56 so far |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 72 | [50] 33 so far |  | Rig Service |  |  | K+ | 0 | Mg/l |
| WOB (kg) | 15 | 15 |  | Pick up BHA |  |  | Chlorides | 5600 | Mg/l |
| RPM | 90 | 90 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | 5/5/LT/MG/6F/4/CD/TQ | in |  | Repair rig |  |  | KCL | 0 | % by wt |
| Impact Force | 648 | 821 |  | Wait On Cement |  |  | Daily Cost $ |  |
| Jet Velocity | 334 | 373 |  | Test BOPs |  |  | Cum Cost $ | 57023.40 |
| B.H.A.: | 216mm Bit-Bit Sub-NMDC-1 x 6-1/4 DC-15 x 6-1/4 DC-JARS-1 x 6-1/4 DC-4 HWDP - |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 30 | ° at | 1486 | m |  | Type | Amount |
| 0000 | 1700 | Jarring pipe – attempt to work free |  | 25 | ° at | 1581 | m |  | Biocide | 0 |
|  |  | Regular derrick inspections |  | 15 | ° at | 1694 | m |  | Pac - L | 0 |
| 1700 |  | Hold S/M – attempt to remove bull plug from swivel |  | 11.5 | ° at | 1759 | m |  | Pac - R | 0 |
|  | 2200 | No go - Remove Goose neck and kelly hose - |  | 23½ | ° at | 1186 | m |  | Barite | 80 |
| 2200 | 2400 | Rig up wire line hold S/M Rih to locate free point |  | 24 | ° at | 1206 | m |  | Xanthum gum | 1 |
|  |  |  |  | 26 | ° at | 1281 | m |  | PHPA/ KCL | 0 |
|  |  |  |  | 31 | ° at | 1354 | m |  | Caustic Soda | 0 |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 108 | mm |  | Liner | 108 | mm |
|  |  |  |  | Pressure | 10,000 | kPa |  | Pressure | 10,000 | KPa |
|  |  |  |  | A.V. DP | 163 | f/min |  | A.V. DP |  | f/min |
|  |  |  |  | A.V. DC | 255 | f/min |  | A.V. DC |  | f/min |
|  |  |  |  | SPM | 95 |  | SPM | 95 |
|  |  | 2 loads of water used today Total 41 |  | GPM | 200 |  | GPM | 200 |
|  |  | 10k rec 28/6 |  |  |  |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton | 50% Excess |  | Size | 244 | mm |
|  |  |  |  | Class Bulk | 506 |  | Weight | 52.48 | Kg/m |
|  |  |  |  | % | NF6 Lead | 0.015g/sk |  | Grade | K-55 |  |
|  |  |  |  | % | Econolite Lead | 0.580g/sk |  | Connection | BTC |  |
|  |  | Held pre-tour safety and job meetings |  | % | NF6 Tail | 0.006g/sk |  | Joints | 47 |  |
|  |  |  |  | % | HR-6L Tail | 0.025g/sk |  | Length | 466.14 | m |
| Days since | LTA | 398 |  | Av. Wt Lead/Tail | 12.5p/g /15.6p/g |  | Depth | 572 m from RKB | m |

,66