LAKES OIL N.L. A.C.N. (004 247 214) BOUNDARY CREEK No.2 PEP 157

DAILY GEOLOGICAL REPORT No. 15 Date: 24-10-2005

Depth: 1100m Progress: 0m Days from Spud: 15

Rig: HUNT RIG No.2 GL(AHD): 74.0m Drilling Rep: Lou DeVattimo RT: (datum) 77.65m Geologist: David Horner Last Casing: 178mm at 1097m

0600 hrs Update: Continue RIH, shut down rig due to inebriated crew.

Comments: Nipple up and pressure test BOP's, RIH with 3.5" drill string and 6.125" (156mm) bit.

| Interval (mRT) | Hydrocarbon Show Summary | Gas |
| --- | --- | --- |
|  | No new formation drilled. |  |

| Formation Tops: | Prognosed (mRT) | Actual* (mRT) | Actual* (mSS) | Difference* (High/Low) |
| --- | --- | --- | --- | --- |
| LaTrobe Group Strzelecki Formation T.D. | 4.7 197 2500 | 4.7 227 | +73 -149 | 0 30 Low |

*Provisional, based on mudlog

LAKES OIL N.L. A.C.N. (004 247 214) BOUNDARY CREEK No.2 PEP 157

DAILY GEOLOGICAL REPORT No. 15

| Lithological and Fluorescence Description |
| --- |
| Interval (m) | Description |
|  | No new formation drilled. |