LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 2 | DFS: | 1 | DATE : | 11-Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 71.00m | LAST DEPTH : | 43.00m | 24 HR PROGRESS : | 28.00m | PTD : | 2500m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 27,342 | CUM. COST : $ | 239,127 |
| 0600 OPS : | W.O.C cement plug |
| Next 24 hr OPS: | Tag cement plug-fill hole with mud –drill ahead if no losses –set another cement plug if losses |
| Site Personnel: | Lakes 3- A.M.C 1- Mud logger 2- Hunt Energy 17 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 Re-Run |  |  | Drilling | 3.00 |  | Density | 8.65 | ppg |
| Size (mm) | 311 |  |  | Tripping | 3.00 |  | Viscosity | 49 | Sec |
| Make | BBL |  |  | Surveys |  |  | PV @ Deg C | 13 | Deg C |
| Type | M-22 |  |  | Rigging up |  |  | YP lbs/100 ft 2 | 15 | Lbs/100ft |
| IADC Code | 1-1-7 |  |  | Slip and cut block line |  |  | API Filtrate |  | m/30min |
| Serial Number | 6093062 |  |  | Circulate and clean hole | 12.00 |  | Gels lbs/100 ft 2 | 8 / 16 /17 |  |
| Nozzles (32) | 18-18-18 |  |  | Cement casing |  |  | Cake 32nds/ in | 3 |  |
| Depth in (m) | 15.00 |  |  | Rig repair |  |  | Sand | 0.25 | % Vol |
| Depth out (m) |  |  |  | Surveys |  |  | Solids | 5.0 | % Vol |
| Total Metres | 56 |  |  | Run Casing |  |  | Hardness Ca mg/l |  |  |
| Hours | 5 |  |  | Rig Service |  |  | KCL Concentration |  | % by wt |
| WOB (kg) | 1000 |  |  | BOP test FIT |  |  | Chlorides |  | Mg/l |
| RPM | 60 |  |  | Drill out Cmt |  |  | Methyl Blue |  | Ppb equiv |
| Condition |  |  |  | Logging |  |  | K+ |  | Mg/l |
| Impact Force | 21lb/ft |  |  | W.0.C |  |  | Daily Cost $ | 1,535 |
| Jet Velocity | 45ft/sec |  |  | Cement plug | 6.00 |  | Cum Cost $ | 3,795 |
| B.H.A.: |  |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 00:00 | 01:00 | Mixed loss circulation material pill |  |  | ° at |  | m |  | Ausgel | 124 |
| 01:00 | 02:00 | Drilled 311mm hole from 43m to 45m no returns |  |  | ° at |  | m |  | L.C.M ( chaff) | 12 |
| 02:00 | 02;30 | Mixed and spotted L.C.M pill at 45m |  |  | ° at |  | m |  | L.C.M (lucerne) | 7 |
| 02:30 | 07:30 | Built up volume in mud pits |  |  | ° at |  | m |  | Sawdust | 1 cubic metre |
| 07:30 | 08:00 | Attempted to circulate pumped 50 bbls mud |  |  | ° at |  | m |  |  |  |
| 08:00 | 08:30 | Pulled out the drilling assembly |  |  | ° at |  | m |  |  |  |
| 08:30 | 11:30 | Poured 15 sax cement and 19 sacks of chaff in hole |  |  | ° at | 1713 | m |  |  |  |
| 11:30 | 12:00 | Tagged at 17m with 311mm bit |  |  |  |  |
| 12:00 | 13:30 | Circulated and cleaned hole to 45m then lost circ |  | PUMP 1 |  | PUMP 2 |
| 13:30 | 14:00 | Drilled 311mm hole from 45m to 49m with no returns |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 14:00 | 16:00 | Built up mud volume in tanks |  | Pressure | 700 | kPa |  | Pressure | 10,500 | KPa |
| 16:00 | 16:30 | Drilled 311mm hole from 49m to 51m with no returns |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
| 16:30 | 17:30 | Built up mud volume in tanks |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
| 17:30 | 18:00 | Drilled 311mm hole from 51m to 71m with no returns |  | SPM |  |  | SPM |  |
| 18:00 | 19:30 | Pulled out of hole , layed out 4 drill collars |  | GPM |  |  | GPM |  |
| 19:30 | 21:00 | Tripped in hole to 66m with open ended drill pipe |  |  |  |  |
| 21:00 | 23:00 | Rigged up Halliburton |  | CEMENT DATA |  | LAST CASING |
| 23:00 | 24:00 | Set 34bbl cement plug at 66m to seal off loss zone |  | Sacks | 20 |  | Size | 340mm |  |
|  |  |  |  | Class |  |  | Weight | 71.43 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | Buttress |  |
|  | JSA |  |  | % |  |  |  | Joints | 1 |  |
|  | JSA |  |  | % |  |  |  | Length | 12.00 | m |
| Days since | LTA |  |  |  |  |  | Shoe |  | m |

,66