LAKES OIL N.L.

DAILY DRILLING REPORT

| WELL: Boundary Creek No.2 | REPORT No.: 39 | DATE: 17-11-2005 |
| --- | --- | --- |
| DFS: 38 | 2400 DEPTH: 2341m | Last Depth: 2341m |
| 24hr Progress: 18m | PTD: 2500m | Total Fuel: 8,600 |
| Fuel Usage: 1,800lt | Daily Cost : $27,423 | Cum Cost: $1,857,174 |
| 0600hrs Operation: | Baker Atlas loggers rigging up to run logs |
| Next 24hr Operation: | Run logs on wireline |
| Site Personnel: | Lakes 3, AMC 1, Higgins 2, Hunt 19 |

| HOURLY OPERATIONS SUMMARY (000-2400hrs) | OPERATIONS BREAKDOWN |
| --- | --- |
| FROM | TO | OPERATION | Drilling | 11.00 |
| 00:00 | 05:30 | Tripped out for Bit change | Tripping | 10.50 |
| 05:30 | 06:00 | Changed bits and cleaned out junk sub no metal | Surveys |  |
| 06:00 | 07:00 | Tripped in hole to 212m | Reaming |  |
| 07:00 | 08:30 | Slipped and cut block line | Slip & Cut Block Line | 1.50 |
| 08:30 | 12:00 | Tripped in hole to 2316m | Circulate & Clean Hole | 1.00 |
| 12:00 | 12:30 | Picked up Kelly washed to bottom at 2323m | Cement Casing |  |
| 12:30 | 23:30 | Drilled 152.4mm hole from 2323m to 2341m | Rig Repair |  |
| 23:30 | 24:00 | Pumped pill racked back the Kelly | Surveys |  |
|  |  |  | Run Casing |  |
|  |  |  | Rig Service |  |
|  |  |  | Test BOP’s |  |
|  |  |  | Drill Out Cement |  |
|  |  |  | Logging |  |
|  |  |  | W.O.C. |  |
|  |  |  | Cement Plug |  |
|  |  |  | Wait on Cementer |  |
|  |  |  | Make up Fishing Tools |  |

| BIT INFORMATION | MUD PROPERTIES |
| --- | --- |
| Bit Number | 8 | Re-Run | Density (ppg) | 9.40 |
| Run Number | 18 | 19 | Viscosity (Sec) | 41 |
| Size (mm) | 152.4 | 152.4 | PV @ Degree C | 13 |
| Make | Reed | Hughes | YP (lbs/100ft2) | 11 |
| Type | SL53ADHT | MX 18H | API Filtrate (ml/30min) | 7.8 |
| IADC Code | 5-3-7 | 4-4-5 | Gels (lbs/100ft2) | 3 / 4 / 5 |
| Serial Number | MX8935 | 5041994 | Filter Cake (32nds inch) | 1/- |
| Nozzles (x32) | 13-14-20 | 16-20-20 | Sand (% Vol) | 0.20 |
| Depth In (m) | 2285 | 2323 | Solids (% Vol) | 7.9 |
| Depth Out (m) | 2323 | 2341 | Hardness (Ca mg/l) | 80 |
| Total Meters | 38 | 18 | KCl (% by wt) | 1.33 |
| Hours | 25.5 | 11.00 | Chlorides (Mg/l) | 9,700 |
| WOB (kg) | 8,000 | 8000 | Methyl Blue (ppg eq) | 7.5 |
| RPM | 80 | 80 | Potassium (Mg/l) | 7,100 |
| Condition | 2-2-ER-C-E | -I-NO-PR | Daily Cost ($) | 656 |
| Impact Force |  | 76lb/ft | Cumulative Cost ($) | 55,019 |
| Jet Velocity |  | 79ft/sec |  |  |

LAKES OIL N.L.

DAILY DRILLING REPORT NO.    39

| CEMENT DATA | LAST CASING | CHEMICALS USED |
| --- | --- | --- |
| Sacks |  | Size | 178mm | AMC Defoamer | 2 |
| Class |  | Weight | 38.69 | Biocide | 1 |
|  |  | Joints | 92 | Barite | 16 |
|  |  | Length | 1092.15m | Caustic | 1 |
|  |  | Shoe | 1097.00m | Sodium sulphite | 1 |
|  |  |  |  | Sodium Bicarbonate | 2 |
|  |  |  |  | Cepac-R | 3 |
|  |  |  |  | Potassium Chloride | 2 |
| SURVEYS | PUMP No.1 | PUMP No.2 |
| 9.5 degrees at 1575m | Liner | 140 mm | Liner |  |
| 7.9 degrees at 1880m | Stroke | 16 inch | Stroke |  |
| 8.0 degrees at 1956m | Pressure | 8,970 KPA | Pressure |  |
| 6.4 degrees at 2146m | A.V. DP | 192 ft/min | A.V. DP |  |
|  | A.V. DC | 281 ft/min | A.V. DC |  |
|  | SPM | 38 | SPM |  |
|  | GPM | 188 | GPM |  |

| OCCUPATIONAL HEALTH AND SAFETY |
| --- |
| Pre tour meeting on wireline |  |  |
| logging |  |  |

| BHA: | Bit-Junk Sub - 2x4¾75” Drill Collars - 14x4¾” Drill Collars – Jars - 2x4¾” Drill Collars |
| --- | --- |
| DAYS SINCE LAST LTA: | 379 |
| COMMENTS: | Slow drill rate due to hard formation |
| REPORT BY: | Lou De-Vattimo |