LAKES OIL N.L.

DAILY DRILLING REPORT

| WELL: Boundary Creek No.2 | REPORT No.: 41 | DATE: 19-11-2005 |
| --- | --- | --- |
| DFS: 40 | 2400 DEPTH: 2341m | Last Depth: 2341m |
| 24hr Progress: 0m | PTD: 2500m | Total Fuel: 6,300 |
| Fuel Usage: 500 | Daily Cost : $ 27,267 | Cum Cost: $1,884,441 |
| 0600hrs Operation: | Baker Atlas running logs |
| Next 24hr Operation: | Run logs on wireline and velocity surveys |
| Site Personnel: | Lakes 4, AMC 1, Higgins 2, Hunt 19 Baker Atlas 6 Expertest 1 |

| HOURLY OPERATIONS SUMMARY (000-2400hrs) | OPERATIONS BREAKDOWN |
| --- | --- |
| FROM | TO | OPERATION | Drilling |  |
| 00:00 | 06:00 | Run log # 2 CBIL | Tripping |  |
| 06:00 | 08:00 | Rigged down tools and made up VSB check tool | Surveys |  |
| 08:00 | 16:00 | Run log # 3 VSB check tool | Reaming |  |
| 16:00 | 17:00 | Rigged down tools | Slip & Cut Block Line |  |
| 17:00 | 24:00 | Made up NMR tools and ran same | Circulate & Clean Hole |  |
|  |  |  | Cement Casing |  |
|  |  |  | Rig Repair |  |
|  |  |  | Surveys |  |
|  |  |  | Run Casing |  |
|  |  |  | Rig Service |  |
|  |  |  | Test BOP’s |  |
|  |  |  | Drill Out Cement |  |
|  |  |  | Logging | 24:00 |
|  |  |  | W.O.C. |  |
|  |  |  | Cement Plug |  |
|  |  |  | Wait on Cementer |  |
|  |  |  | Make up Fishing Tools |  |

| BIT INFORMATION | MUD PROPERTIES |
| --- | --- |
| Bit Number | Re run |  | Density (ppg) | 9.40 |
| Run Number | 19 |  | Viscosity (Sec) | 44 |
| Size (mm) | 152.4 |  | PV @ Degree C | 15 |
| Make | Hughes |  | YP (lbs/100ft2) | 14 |
| Type | MX 18H |  | API Filtrate (ml/30min) | 7.8 |
| IADC Code | 4-4-5 |  | Gels (lbs/100ft2) | 2 / 3 / 4 |
| Serial Number | 5041994 |  | Filter Cake (32nds inch) | 1/- |
| Nozzles (x32) | 16-20-20 |  | Sand (% Vol) | 0.10 |
| Depth In (m) | 2323 |  | Solids (% Vol) | 7.9 |
| Depth Out (m) | 2341 |  | Hardness (Ca mg/l) | 60 |
| Total Meters | 18 |  | KCl (% by wt) | 1.42 |
| Hours | 11.00 |  | Chlorides (Mg/l) | 9,700 |
| WOB (kg) | 8,000 |  | Methyl Blue (ppg eq) | 7.5 |
| RPM | 80 |  | Potassium (Mg/l) | 7,500 |
| Condition | 2-2-NO-A- | E-I-NO-LOG | Daily Cost ($) | 0 |
| Impact Force |  |  | Cumulative Cost ($) | 55,019 |
| Jet Velocity |  |  |  |  |

LAKES OIL N.L.

DAILY DRILLING REPORT NO.    40

| CEMENT DATA | LAST CASING | CHEMICALS USED |
| --- | --- | --- |
| Sacks |  | Size | 178mm |  |  |
| Class |  | Weight | 38.69 |  |  |
|  |  | Joints | 92 |  |  |
|  |  | Length | 1092.15m |  |  |
|  |  | Shoe | 1097.00m |  |  |
| SURVEYS | PUMP No.1 | PUMP No.2 |
| 9.5 degrees at 1575m | Liner | 140 mm | Liner |  |
| 7.9 degrees at 1880m | Stroke | 16 inch | Stroke |  |
| 8.0 degrees at 1956m | Pressure |  | Pressure |  |
| 6.4 degrees at 2146m | A.V. DP |  | A.V. DP |  |
|  | A.V. DC |  | A.V. DC |  |
|  | SPM |  | SPM |  |
|  | GPM |  | GPM |  |

| OCCUPATIONAL HEALTH AND SAFETY |
| --- |
| Pre tour meeting on wireline |  |  |
| logging |  |  |

| BHA: | Bit-Junk Sub - 2x4¾75” Drill Collars - 14x4¾” Drill Collars – Jars - 2x4¾” Drill Collars |
| --- | --- |
| DAYS SINCE LAST LTA: | 381 |
| COMMENTS: |  |
| REPORT BY: | Lou De-Vattimo |