LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 17 | DFS: | 16 | DATE : | 27 Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1244m | LAST DEPTH : | 1147m | 24 HR PROGRESS : | 97m | PTD : | 2500m |
| TOTAL FUEL : | 6,900 | FUEL USAGE : | 700 |  | 53,359 | CUM. COST : $ | 1,173,560 |
| 0600 OPS : | Trip out to change Bottom hole drilling assembly for deviation control |
| Next 24 hr OPS: | Trip in hole drill ahead to drop deviation angle thru fault zone |
| Site Personnel: | Lakes 3 A.M.C 1- Mud logger 2- Hunt Energy 19 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 6 |  |  | Drilling | 23.00 |  | Density | 9.35 | ppg |
| Size (mm) | 156 |  |  | Tripping |  |  | Viscosity | 40 | Sec |
| Make | Reed |  |  | Surveys | 0.50 |  | PV @ Deg C | 13 | Deg C |
| Type | SL43HP |  |  | Reaming |  |  | YP lbs/100 ft 2 | 13 | Lbs/100ft |
| IADC Code | 4-3-7 |  |  | Slip and cut block line |  |  | API Filtrate | 7.0 | m/30min |
| Serial Number | JK 4699 |  |  | Circulate and clean hole | 0.50 |  | Gels lbs/100 ft 2 | 2/3/5 |  |
| Nozzles (32) | 13-14-16 |  |  | Cement casing |  |  | Cake 32nds/ in | 1 |  |
| Depth in (m) | 1100 |  |  | Rig repair |  |  | Sand | 0.15 | % Vol |
| Depth out (m) |  |  |  | Off payroll |  |  | Solids | 7.4 | % Vol |
| Total Metres | 144 |  |  | Run Casing |  |  | Hardness Ca mg/l | 280 |  |
| Hours | 34 |  |  | Rig Service |  |  | KCL Concentration | 1.75 | % by wt |
| WOB (kg) | 7000 |  |  | Test BOP |  |  | Chlorides | 10,000 | Mg/l |
| RPM | 100 |  |  | Drill out Cmt |  |  | Methyl Blue | 8.5 | Ppb equiv |
| Condition |  |  |  | Logging |  |  | K+ | 9,300 | Mg/l |
| Impact Force | 166lb/ft |  |  | W.0.C |  |  | Daily Cost $ | 1,552 |
| Jet Velocity | 150ft/sec |  |  | Install BOP |  |  | Cum Cost $ | 28,847 |
| B.H.A.: | Bit- Near bit stab- 2 x 4-3/4inch drill collars- stabilizer -11 x 4-3/4inch drill collars-Jars-2 x 4-3/4 inch drill collars -4 x Hevi-Wate drillpipe |
|  | BHA length Weight below Jars |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 0.25 | ° at | 218m | m |  | Type | Amount |
| 00:00 | 18:30 | Drilled156mm hole from1147m to1225m |  | 1.50 | ° at | 600m | m |  | Defoamer / Biocide |  |
| 18:30 | 19:00 | Circulated hole clean |  | 2.00 | ° at | 797m | m |  | Caustic | 1 |
| 19:00 | 19:30 | Ran survey at 1214m |  | 2.50 | ° at | 938m | m |  | AMC PAC-L / R | 1 / 5 |
| 19:30 | 24:00 | Drilled 156mm hole from 1225m to 1244m |  | 3.00 | ° at | 1096m | m |  | Xanthum gum | 1 |
|  |  |  |  | 6.00 | ° at | 1214m | m |  | Potassium chloride | 10 |
|  |  |  |  |  | ° at |  | m |  | Soium Bicarbonate | 1 |
|  |  |  |  |  | ° at |  | m |  | Sodium sulphite | 2 |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 7,700 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 96 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 45 |  | SPM |  |
|  |  |  |  | GPM | 223 |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks |  |  | Size | 178mm |  |
|  |  |  |  | Class |  |  | Weight | 38.69 | Kg/m |
|  |  |  |  |  |  |  |  | Grade | N-80 |  |
|  |  |  |  |  |  |  |  | Connection | Buttress |  |
|  | JSA | Company policies and flow check on connections |  |  |  |  |  | Joints | 92 |  |
|  |  |  |  |  |  |  |  | Length |  | m |
| Days since | LTA | 358 |  |  |  |  | Shoe | 1097 | m |

,66