LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Boundary creek-2 | REPORT No. : | 18 | DFS: | 17 | DATE : | 27 Oct-05 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1268m | LAST DEPTH : | 1244m | 24 HR PROGRESS : | 24m | PTD : | 2500m |
| TOTAL FUEL : | 2,850 | FUEL USAGE : | 2,150 |  | 27,740 | CUM. COST : $ | 1,201,300 |
| 0600 OPS : | Survey at 1282m |
| Next 24 hr OPS: | Drill ahead - Bit change if drill rate too slow |
| Site Personnel: | Lakes 3 A.M.C 1- Mud logger 2- Hunt Energy 19 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 6 | 7 Re-Run |  | Drilling | 9.00 |  | Density | 9.35 | ppg |
| Size (mm) | 156 | 156 |  | Tripping | 9.50 |  | Viscosity | 39 | Sec |
| Make | Reed | Varel |  | Surveys | 2.00 |  | PV @ Deg C | 39 | Deg C |
| Type | SL43HP | M-332 |  | Reaming |  |  | YP lbs/100 ft 2 | 8 | Lbs/100ft |
| IADC Code | 4-3-7 |  |  | Slip and cut block line |  |  | API Filtrate | 7.4 | m/30min |
| Serial Number | JK 4699 | MSK56G1 |  | Circulate and clean hole | 3.50 |  | Gels lbs/100 ft 2 | 2 / 3 / 5 |  |
| Nozzles (32) | 13-14-16 | 14-14-14 |  | Cement casing |  |  | Cake 32nds/ in | 1 |  |
| Depth in (m) | 1100 | 1244 |  | Rig repair |  |  | Sand | 0.25 | % Vol |
| Depth out (m) | 1244 |  |  | Off payroll |  |  | Solids | 7.4 | % Vol |
| Total Metres | 144 | 24 |  | Run Casing |  |  | Hardness Ca mg/l | 120 |  |
| Hours | 34 | 9 |  | Rig Service |  |  | KCL Concentration | 1.67 | % by wt |
| WOB (kg) | 7000 | 5000 |  | Test BOP |  |  | Chlorides | 9,600 | Mg/l |
| RPM | 100 | 120 |  | Drill out Cmt |  |  | Methyl Blue | 9.0 | Ppb equiv |
| Condition |  |  |  | Logging |  |  | K+ | 8,900 | Mg/l |
| Impact Force | 166lb/ft |  |  | W.0.C |  |  | Daily Cost $ | 1,093 |
| Jet Velocity | 150ft/sec |  |  | Install BOP |  |  | Cum Cost $ | 29,940 |
| B.H.A.: | Bit- Bit sub- 2 x 4-3/4inch drill collars- stabilizer -11 x 4-3/4inch drill collars-Jars-2 x 4-3/4 inch drill collars -4 x Hevi-Wate drillpipe |
|  | BHA length Weight below Jars |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 1.50 | ° at | 600m | m |  | Type | Amount |
| 00:00 | 02:00 | Circulated hole clean |  | 2.00 | ° at | 797m | m |  | Defoamer / Biocide | 1 / 1 |
| 02:00 | 02:30 | Ran survey on wireline at 1243m |  | 2.50 | ° at | 938m | m |  | Barite | 10 |
| 02:30 | 03:00 | Pumped pill |  | 3.00 | ° at | 1096m | m |  | Starlose | 4 |
| 03:00 | 03;30 | Pulled back to 1195m |  | 4.25 | ° at | 1147m | m |  | Xanthum gum | 1 |
| 03:30 | 04:00 | Ran survey on wireline at 1195m |  | 5.00 | ° at | 1195m | m |  | Potassium chloride | 8 |
| 04:00 | 04:30 | Pulled back to 1147m |  | 6.00 | ° at | 1214m | m |  | Soium Bicarbonate | 2 |
| 04:30 | 05:00 | Ran survey on wireline at 1147m |  | 6.50 | ° at | 1243m | m |  | Sodium sulphite | 1 |
| 05:00 | 08:00 | Tripped out to change BHA |  |  |  |  |
| 08;00 | 09:00 | Changed bits ,layed out near bit stabilzer |  | PUMP 1 |  | PUMP 2 |
| 09:00 | 13:00 | Tripped in hole to 1108m |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 13:00 | 13:30 | Filled pipe with mud |  | Pressure | 7,700 | kPa |  | Pressure |  | KPa |
| 13;30 | 14:00 | Tripped in hole to 1244m |  | A.V. DP | 221 | ft/min |  | A.V. DP |  | m/min |
| 14;00 | 21:00 | Drilled 156mm hole from 1244m to 1263m |  | A.V. DC | 323 | ft/min |  | A.V. DC |  | m/min |
| 21:00 | 21:30 | Circulated |  | SPM | 46 |  | SPM |  |
| 21:30 | 22:00 | Ran survey at 1261m 7 deg |  | GPM | 228 |  | GPM |  |
| 22:00 | 24:00 | Drilled 156mm hole from 1263m to 1268m |  |  |  |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  | Control drilling wt on bit to drop angle on bottom |  | Sacks |  |  | Size | 178mm |  |
|  |  |  |  | Class |  |  | Weight | 38.69 | Kg/m |
|  |  |  |  |  |  |  |  | Grade | N-80 |  |
|  |  |  |  |  |  |  |  | Connection | Buttress |  |
|  | JSA | Making connections |  |  |  |  |  | Joints | 92 |  |
|  |  | Rigging up fill up line |  |  |  |  |  | Length |  | m |
| Days since | LTA | 358 |  |  |  |  | Shoe | 1097 | m |

,66