## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-09-19
1
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 84 |  |  | 24 HR PROG | 84 |  |  |  | CUM. COSTS | 1312923.67
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Limestone | Dann/Porter/Webb | Dann/Porter/Webb | PTD | 2075 |  |  |  | DAILY COSTS | 1312923.67
OP's TO 06:00 |  | Drill 12 1/4" hole from 84m to 176m
REMARKS: |  | No PVT working, Flow show system 50%. Incident during connection involving Leigh Walton. Non injury. | [10 empty] | PERSONNEL ON SITE: |  |  | 37
LAST CASING |  | 20 | SET AT | 27 | LOT |  | MAASP |  |  |  |  | BOP TEST | NIL |  | TEST DUE
53 |  | SAFETY | 1. Drilling mouse and rat hole, Stair safety, 3 points of contact | [10 empty] | WEATHER AM | Clear and cold
|  |  | 2. Picking up BHA, operating tongs, team work, communication. | [10 empty] | PM | Clear and cold
BIT INFORMATION |  |  |  | 1 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0-10 | JET V(fps) |  | TOOL |  |  | LENGTH |  | Time | 23:30 |  |  | Casing |  |  | 0
RPM | 120 | H S I |  | Bit |  |  | 0.3 |  | Depth (m) | 84 |  |  | Cementing |  |  | 0
BIT NUMBER |  | 1 | A | Bit Sub |  |  | 0.94 |  | Temp (° C) | 19 |  |  | Circ & Condition |  |  | 0
Size (in) |  | 12.25 | 0 | Ander drift |  |  | 3.01 |  | Mud Type | Spud |  |  | Coring |  |  | 0
Make |  | Varel | 0 | Drill collars x 2 |  |  | 18.47 |  | Density (ppg) | 8.8 |  |  | D/O Cement |  |  | 0
Type |  | CH1GMS | 0 | X/O |  |  | 0.79 |  | ECD (ppg) |  |  |  | Drilling |  | 3.5 | 3.5
IADC Code |  | 117 | 0 | Stab |  |  | 1.41 |  | Viscosity (sec) | 42 |  |  | Handle BHA |  |  | 0
Serial Number |  | 198598 | 0 | X/O |  |  | 0.79 |  | PV / YP (cp/lb) | 10 / 19 |  |  | LOT / FIT |  |  | 0
T.F.A.( ") |  | 0.58905 | 0 | Drill Collar x 14 |  |  | 128.83 |  | Gells (s/m) | 6 / 12 |  |  | N/U & Test BOP's |  |  | 0
Depth In (m) |  | 27 | 0 | Hwdp x 4 |  |  | 37.55 |  | API Filt. (cc) |  |  |  | P & A |  |  | 0
Depth Out (m) |  | IN | 27 | [5 empty] | Cake (/32") |  |  |  | Repairs |  |  | 0
Total Meters |  | 57 | 27 | [5 empty] | Solids (% Vol) | 2 |  |  | Rig Move |  |  | 0
Hours |  | 3.5 | 0 | [5 empty] | Sand (% Vol) | 0.25 |  |  | Rig Service |  |  | 0
ROP |  | 16.2857 | [6 empty] | MBT | 20 |  |  | Safety |  | 2.5 | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 192.09 |  | pH (strip) | 9.5 |  |  | Survey |  |  | 0
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 41.4353 |  | Chlorides (mg/l) |  |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 0 |  | STRING WT (kLb) |  |  | 35.6494 |  | KCL (% ) |  |  |  | Tripping |  |  | 0
AV - DP (fpm) |  | 0 |  | HOOK LOAD (kLb) |  |  | 35 |  | PHPA (ppb) |  |  |  | Wait on Cement |  |  | 0
AV - DC (fpm) |  | 0 |  | WT BELOW JARS (kLb) |  |  | 0 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  |  | 0
SPP (psi) |  | 1100 |  | DRAG UP (kLb) |  |  |  |  | Circ. Vol. (Bbl) | 361 |  |  | Well Control |  |  | 0
SPP (calculated) |  |  |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 1-2 |  | Caustic Soda |  | 2 |  | Wellhead |  |  | 0
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  |  |  | Trugel 13A |  | 225 |  | Wiper Trip |  |  | 0
RATE | 0 | RATE | 0 | ENVIRONMENTAL DATA |  |  |  |  | Soda Ash |  | 3 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 44250 | [6 empty] | Other |  | 18 | 18
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | -44250 | [6 empty] | TOTALS |  | 24 | 24
|  |  |  | CUM. FUEL USED |  | -44250 | [6 empty] | DAILY MUD COSTS |  | 1996.67
SURVEYS |  |  |  | CUM. MUD MIXED |  | 564 | [6 empty] | CUM. MUD COSTS |  | 1996.67
0° at 50m |  |  |  | CUM. MUD LOSSES |  | 70 | [6 empty] | AFE COST - C&S |  | 2847416
0° at 102m |  |  |  | CUM. GEL |  | 5625 | [6 empty] | AFE COST - P&A |  | 2588872
0° at 148m |  |  |  | CUM. BARITES |  | 0 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 18:00 | Complete rig up of drilling equipment. Note no PVT or Flow show equipment operational.
18:00 | 20:30 | Spud Childers cove and commence drilling 12 1/4" hole from 27m to 74m. Take survey at 50m, zero on Anderdrift
20:30 | 23:00 | Incident during connection on rig floor involving Leigh Walton. Non injury
23:00 | 24:00 | Continue to drill 12 1/4" hole from 74m to 84m
| SUPERVISOR: | Dann/Porter/Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #1