## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-09-22
4
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 550.001 |  |  | 24 HR PROG | 0 |  |  |  | CUM. COSTS | 1560709.65
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Gellibrand Marl | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 49789.5
OP's TO 06:00 |  | Commence Installation of weld on A section, complete at 5am. Cooling.
REMARKS: |  | "A" section on location at 23:00hrs | [10 empty] | PERSONNEL ON SITE: |  |  | 38
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 0 | MAASP |  |  |  |  | BOP TEST | NIL |  | TEST DUE
56 |  | SAFETY | 1. Nippling up BOPs, Mud pump module Repairs | [10 empty] | WEATHER AM | Overcast
|  |  | 2. Nippling up BOPs, Mud pump module Repairs | [10 empty] | PM | Overcast
BIT INFORMATION | [8 empty] | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0 | JET V(fps) |  | TOOL |  |  | LENGTH |  | Time | Mixing |  |  | Casing |  |  | 8
RPM | 0 | H S I | [6 empty] | Depth (m) | 550 |  |  | Cementing |  |  | 1.5
BIT NUMBER |  |  | 0 | [5 empty] | Temp (° C) |  |  |  | Circ & Condition |  |  | 3
Size (in) | [8 empty] | Mud Type | KCL/PHPA |  |  | Coring |  |  | 0
Make | [8 empty] | Density (ppg) | mixing |  |  | D/O Cement |  |  | 0
Type | [8 empty] | ECD (ppg) |  |  |  | Drilling |  |  | 26
IADC Code | [8 empty] | Viscosity (sec) |  |  |  | Handle BHA |  |  | 0
Serial Number | [8 empty] | PV / YP (cp/lb) |  |  |  | LOT / FIT |  |  | 0
T.F.A.( ") | [8 empty] | Gells (s/m) |  |  |  | N/U & Test BOP's |  | 17.5 | 17.5
Depth In (m) | [8 empty] | API Filt. (cc) |  |  |  | P & A |  |  | 0
Depth Out (m) | [8 empty] | Cake (/32") |  |  |  | Repairs |  |  | 0
Total Meters | [8 empty] | Solids (% Vol) |  |  |  | Rig Move |  |  | 18
Hours | [8 empty] | Sand (% Vol) |  |  |  | Rig Service |  |  | 1
ROP | [8 empty] | MBT |  |  |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 0 |  | pH (strip) |  |  |  | Survey |  |  | 0
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 0 |  | Chlorides (mg/l) |  |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 0 |  | STRING WT (kLb) |  |  |  |  | KCL (% ) |  |  |  | Tripping |  |  | 4
AV - DP (fpm) |  | 0 |  | HOOK LOAD (kLb) |  |  |  |  | PHPA (ppb) |  |  |  | Wait on Cement |  | 1.5 | 3.5
AV - DC (fpm) |  | 0 |  | WT BELOW JARS (kLb) |  |  | 0 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  |  | 0
SPP (psi) |  |  |  | DRAG UP (kLb) |  |  |  |  | Circ. Vol. (Bbl) |  |  |  | Well Control |  |  | 0
SPP (calculated) |  |  |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  |  |  | Duo-Tec |  | 8 |  | Wellhead |  | 5 | 5
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  |  |  | Glute 25 |  | 1 |  | Wiper Trip |  |  | 5
RATE | 0 | RATE | 0 | ENVIRONMENTAL DATA |  |  |  |  | Polyplus |  | 4 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 36200 |  |  | Polypac UL |  | 8 |  | Other |  |  | 1
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 1400 |  |  | Sod Bicarb |  | 2 |  | TOTALS |  | 24 | 96
|  |  |  | CUM. FUEL USED |  | 13750 |  |  | Pot chloride/KCL |  | 100 |  | DAILY MUD COSTS |  | 5719.5
SURVEYS |  |  |  | CUM. MUD MIXED |  | 1619 | [6 empty] | CUM. MUD COSTS |  | 11568.65
|  |  |  | CUM. MUD LOSSES |  | 1650 | [6 empty] | AFE COST - C&S |  | 2847416
|  |  |  | CUM. GEL |  | 6000 | [6 empty] | AFE COST - P&A |  | 2588872
|  |  |  | CUM. BARITES |  | 0 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 1:30 | Wait on cement
1:30 | 3:30 | Rough cut 9 5/8" casing.
3:30 | 5:00 | Lay out landing joint and cut joint, halliburton head and x/o's.
5:00 | 6:30 | Final cut 9 5/8" casing and dress for slip on SOW 5k Braiden head.
6:30 | 21:00 | Install rental 13 5/8" annular on DBL Bop. Pressure test Choke and Kill manifold. Slip and cut drilling line.
21:00 | 24:00 | Pressure test Kelly hose, Kelly cocks and stand pipe manifiold. 250/2500psi, 5/5mins. Prepare SOW 5k well head
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #4