## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-10-03
15
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 2658 |  |  | 24 HR PROG | 42 |  |  |  | CUM. COSTS | 2290453.86
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Eumeralla | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 48807.47
OP's TO 06:00 |  | Log from 2656.8m to 2400m. Rig down wire line equipment, RIH BHA from derrick to lay out.
REMARKS: |  | 0 | [10 empty] | PERSONNEL ON SITE: |  |  | 38
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  | 447.8182 |  |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
67 |  | SAFETY | 1. Drilling ahead & POH | [10 empty] | WEATHER AM | Fine
|  |  | 2. Racking back DP on floor | [10 empty] | PM | Fine
BIT INFORMATION |  |  |  | 2 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 10-20 | JET V(fps) | 204.3979 | TOOL |  |  | LENGTH |  | Time | 21:00 |  |  | Casing |  |  | 8
RPM | 120 | H S I | 1.8763 | Bit |  |  | 0.27 |  | Depth (m) | 2658 |  |  | Cementing |  |  | 1.5
BIT NUMBER |  | 2RR1 | 0 | Near Bit Stab |  |  | 1.27 |  | Temp (° C) | 63 |  |  | Circ & Condition |  | 2.5 | 9
Size (in) |  | 8.5 |  | Ander drift |  |  | 3.01 |  | Mud Type | KCL/PHPA |  |  | Coring |  |  | 0
Make |  | Hughes |  | Drill collars x 1 |  |  | 9.18 |  | Density (ppg) | 9.6 |  |  | D/O Cement |  |  | 2
Type |  | HC605S |  | String Stab |  |  | 1.35 |  | ECD (ppg) | 10.2369 |  |  | Drilling |  | 7.5 | 165
IADC Code |  | S323 |  | Drill collars x 14 |  |  | 129.26 |  | Viscosity (sec) | 58 |  |  | Handle BHA |  |  | 5.5
Serial Number |  | 7002589 |  | Drilling Jars |  |  | 9.56 |  | PV / YP (cp/lb) | 25 / 33 |  |  | LOT / FIT |  |  | 0.5
T.F.A.( ") |  | 0.79844 |  | Drill Collar x 2 |  |  | 18.04 |  | Gells (s/m) | 5 / 10 |  |  | N/U & Test BOP's |  |  | 43.5
Depth In (m) |  | 2545 |  | Hwdp x 4 |  |  | 37.55 |  | API Filt. (cc) | 5 |  |  | P & A |  |  | 0
Depth Out (m) |  | 2658 | [6 empty] | Cake (/32") | 1 |  |  | Repairs |  |  | 6
Total Meters |  | 113 | [6 empty] | Solids (% Vol) | 9.6 |  |  | Rig Move |  |  | 18
Hours |  | 18 | [6 empty] | Sand (% Vol) | 0.5 |  |  | Rig Service |  | 0.5 | 5.5
ROP |  | 6.2778 | [6 empty] | MBT | 8 |  |  | Safety |  |  | 2.5
Condition Out |  | 3 2 WT N X I NO TD |  | BHA LENGTH (m) |  |  | 209.49 |  | pH (strip) | 9.1 |  |  | Survey |  |  | 1.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 43.8966 |  | Chlorides (mg/l) | 28000 |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 508.6296 |  | STRING WT (kLb) |  |  | 173.1076 |  | KCL (% ) | 5.4 |  |  | Tripping |  | 10 | 53.5
AV - DP (fpm) |  | 239.7406 |  | HOOK LOAD (kLb) |  |  | 190 |  | PHPA (ppb) | 0.75 |  |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 375.6387 |  | WT BELOW JARS (kLb) |  |  | 33.601 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  | 0.5 | 8
SPP (psi) |  | 1950 |  | DRAG UP (kLb) |  |  | 3 |  | Circ. Vol. (Bbl) | 843 |  |  | Well Control |  |  | 0
SPP (calculated) |  | 1900 |  | DRAG DOWN (kLb) |  |  | 3 |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 40-121 |  | Barite |  | 87 |  | Wellhead |  |  | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  | 10-31 |  | Duo-Tec |  | 2 |  | Wiper Trip |  |  | 5
RATE | 84 | RATE | 84 | ENVIRONMENTAL DATA |  |  |  |  | Polyplus |  | -1 |  | Wireline |  | 3 | 12.5
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 16650 |  |  | Polypac UL |  | 1 |  | Other |  |  | 3
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 4350 |  |  | Pot chloride/KCL |  | 14 |  | TOTALS |  | 24 | 360
SCR: 610 @ 70 |  | SCR: 920 @ 100 |  | CUM. FUEL USED |  | 55550 | [6 empty] | DAILY MUD COSTS |  | 1477.47
SURVEYS |  |  |  | CUM. MUD MIXED |  | 4432 | [6 empty] | CUM. MUD COSTS |  | 76045.86
|  |  |  | CUM. MUD LOSSES |  | 4119 | [6 empty] | AFE COST - C&S |  | 2847416
|  |  |  | CUM. GEL |  | 6000 | [6 empty] | AFE COST - P&A |  | 2588872
|  |  |  | CUM. BARITES |  | 12625 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 1:00 | Continue to drill 8 1/2" hole from 2616m to 2620m
1:00 | 1:30 | Change swab in No 1 pump
1:30 | 8:00 | Drill 8-1/2" hole from 2620 to 2658m
8:00 | 9:00 | Circulate hole clean
9:00 | 9:30 | Pump slug & hoist on wiper trip to 2571m
9:30 | 10:00 | Wash & ream up from 2571 to 2552m
10:00 | 10:30 | POOH
10:30 | 11:30 | Run in hole & wash 2 singles to bottom, 4m of fill otherwise hole good
11:30 | 13:00 | Circulate hole clean, spot 250m Hi-Vis pill on bottom, pump slug
13:00 | 21:00 | POOH from 2658m to surface, 30k drag @2561-2543, @1634-1625, @1203-1193m
21:00 | 21:30 | Clean up rig floor, Hold pre task safety meeting and rig up Precision wire line.
21:30 | 24:00 | Run in Hole and log as per program MCG,MDN,MPD,MSS,MLE,MMR.
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #15