## Report
| DAILY DRILLING REPORT | [12 empty] | 2005-10-04
16
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 2658 |  |  | 24 HR PROG | 0 |  |  | CUM. COSTS | 2411933.86
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Eumeralla | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  | DAILY COSTS | 121480
OP's TO 06:00 |  | Take pressure reading #4, tool failure, POOH , run back up tool. Logs complete @05:57
REMARKS: |  | 0 | [9 empty] | PERSONNEL ON SITE: |  |  | 40
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  | 447.8182 |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
68 |  | SAFETY | 1. Logging & tripping | [9 empty] | WEATHER AM | Fine
|  |  | 2. Running in Drill Pipe | [9 empty] | PM | Fine
BIT INFORMATION | [8 empty] | MUD PROPERTIES |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0 | JET V(fps) |  | TOOL |  |  | LENGTH |  | Time | 19:30 |  | Casing |  |  | 8
RPM | 0 | H S I | [6 empty] | Depth (m) | 2658 |  | Cementing |  |  | 1.5
BIT NUMBER |  |  | 0 | [5 empty] | Temp (° C) |  |  | Circ & Condition |  |  | 9
Size (in) | [8 empty] | Mud Type | KCL/PHPA |  | Coring |  |  | 0
Make | [8 empty] | Density (ppg) | 9.6 |  | D/O Cement |  |  | 2
Type | [8 empty] | ECD (ppg) |  |  | Drilling |  |  | 165
IADC Code | [8 empty] | Viscosity (sec) | 58 |  | Handle BHA |  |  | 5.5
Serial Number | [8 empty] | PV / YP (cp/lb) | 26 / 31 |  | LOT / FIT |  |  | 0.5
T.F.A.( ") | [8 empty] | Gells (s/m) | 5 / 10 |  | N/U & Test BOP's |  |  | 43.5
Depth In (m) | [8 empty] | API Filt. (cc) | 5 |  | P & A |  |  | 0
Depth Out (m) | [8 empty] | Cake (/32") | 1 |  | Repairs |  |  | 6
Total Meters | [8 empty] | Solids (% Vol) | 9.2 |  | Rig Move |  |  | 18
Hours | [8 empty] | Sand (% Vol) | 0.5 |  | Rig Service |  | 0.5 | 6
ROP | [8 empty] | MBT | 8 |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 0 |  | pH (strip) | 9 |  | Survey |  |  | 1.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 0 |  | Chlorides (mg/l) | 28000 |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 0 |  | STRING WT (kLb) |  |  |  |  | KCL (% ) | 5.5 |  | Tripping |  | 6.5 | 60
AV - DP (fpm) |  | 0 |  | HOOK LOAD (kLb) |  |  |  |  | PHPA (ppb) | 0.75 |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 0 |  | WT BELOW JARS (kLb) |  |  | 0 |  | ALC - 50 (K) |  |  | Wash / Ream |  |  | 8
SPP (psi) |  |  |  | DRAG UP (kLb) |  |  |  |  | Circ. Vol. (Bbl) | 787 |  | Well Control |  |  | 0
SPP (calculated) |  |  |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) | [7 empty] | Wellhead |  |  | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) | [7 empty] | Wiper Trip |  |  | 5
RATE | 0 | RATE | 0 | ENVIRONMENTAL DATA | [7 empty] | Wireline |  | 12 | 24.5
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 14750 | [5 empty] | Other |  | 5 | 8
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 1900 | [5 empty] | TOTALS |  | 24 | 384
|  |  |  | CUM. FUEL USED |  | 57450 | [5 empty] | DAILY MUD COSTS
SURVEYS |  |  |  | CUM. MUD MIXED |  | 4432 | [5 empty] | CUM. MUD COSTS |  | 76045.86
|  |  |  | CUM. MUD LOSSES |  | 4144 | [5 empty] | AFE COST - C&S |  | 2847416
|  |  |  | CUM. GEL |  | 6000 | [5 empty] | AFE COST - P&A |  | 2588872
|  |  |  | CUM. BARITES |  | 12625 | [5 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 4:00 | Log as per program MCG,MDN,MPD,MSS,MLE,MMR. To a depth of 2656m
4:00 | 4:30 | Rig down Precision loggers
4:30 | 8:30 | Run in hole with BHA then lay it out
8:30 | 10:30 | Pick up 2-7/8" tubing stinger & run in hole to run P & A plugs
10:30 | 11:00 | Slip line
11:00 | 12:30 | Wait on orders
12:30 | 13:00 | Hoist & rack pipe back in derrick
13:00 | 16:30 | Wait on Precision MFT engineer to return to rig, rig up Precision
16:30 | 17:00 | Rig up tools MCG, MFT.
17:00 | 22:30 | RIH and take pressure readings at points #1, 2, 3. Tool failure.
22:30 | 23:00 | Pull to shoe,
23:00 | 23:30 | Cycle tools at shoe, operating ok.
23:30 | 24:00 | RIH MCG, MFT
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | John Hobday |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #16