## Report
| DAILY DRILLING REPORT | [12 empty] | 2005-10-06
18
WELL | Childers Cove 1 |  |  |  | 24:00 DEPTH | 2658 |  |  | 24 HR PROG | 0 |  |  | CUM. COSTS | 2618932.78
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Eumeralla | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  | DAILY COSTS | 75519
OP's TO 06:00 |  | Rig down & prepare to move to Woodside well
REMARKS: |  | Rig release time 20:00hrs. | [9 empty] | PERSONNEL ON SITE: |  |  | 33
LAST CASING |  | 9.625 | SET AT | 544.5 | LOT | 14.4208 | MAASP |  |  |  | BOP TEST | 2005-09-23 |  | TEST DUE | 2005-10-14
70 |  | SAFETY | 1. Cementing & laying out pipe | [9 empty] | WEATHER AM | Fine
|  |  | 2. Nipple down BOPs, complete laying out drill pipe. | [9 empty] | PM | Overcast
BIT INFORMATION | [8 empty] | MUD PROPERTIES |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0 | JET V(fps) |  | TOOL |  |  | LENGTH |  | Time |  |  | Casing |  |  | 8
RPM | 0 | H S I | [6 empty] | Depth (m) |  |  | Cementing |  |  | 1.5
BIT NUMBER |  |  | 0 | [5 empty] | Temp (° C) |  |  | Circ & Condition |  |  | 10
Size (in) | [8 empty] | Mud Type |  |  | Coring |  |  | 0
Make | [8 empty] | Density (ppg) | 0 |  | D/O Cement |  |  | 2
Type | [8 empty] | ECD (ppg) |  |  | Drilling |  |  | 165
IADC Code | [8 empty] | Viscosity (sec) |  |  | Handle BHA |  |  | 5.5
Serial Number | [8 empty] | PV / YP (cp/lb) |  |  | LOT / FIT |  |  | 0.5
T.F.A.( ") | [8 empty] | Gells (s/m) |  |  | N/U & Test BOP's |  | 6.5 | 50
Depth In (m) | [8 empty] | API Filt. (cc) |  |  | P & A |  | 13.5 | 22
Depth Out (m) | [8 empty] | Cake (/32") |  |  | Repairs |  |  | 6
Total Meters | [8 empty] | Solids (% Vol) |  |  | Rig Move |  |  | 18
Hours | [8 empty] | Sand (% Vol) |  |  | Rig Service |  |  | 6
ROP | [8 empty] | MBT |  |  | Safety |  |  | 2.5
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 0 |  | pH (strip) |  |  | Survey |  |  | 1.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 0 |  | Chlorides (mg/l) |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 0 |  | STRING WT (kLb) |  |  |  |  | KCL (% ) |  |  | Tripping |  |  | 65.5
AV - DP (fpm) |  | 0 |  | HOOK LOAD (kLb) |  |  |  |  | PHPA (ppb) |  |  | Wait on Cement |  |  | 3.5
AV - DC (fpm) |  | 0 |  | WT BELOW JARS (kLb) |  |  | 0 |  | ALC - 50 (K) |  |  | Wash / Ream |  |  | 8
SPP (psi) |  |  |  | DRAG UP (kLb) |  |  |  |  | Circ. Vol. (Bbl) |  |  | Well Control |  |  | 0
SPP (calculated) |  |  |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) | [7 empty] | Wellhead |  |  | 6
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) | [7 empty] | Wiper Trip |  |  | 5
RATE | 0 | RATE | 0 | ENVIRONMENTAL DATA | [7 empty] | Wireline |  |  | 31.5
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 8800 | [5 empty] | Other |  |  | 10
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 1100 | [5 empty] | TOTALS |  | 20 | 428
|  |  |  | CUM. FUEL USED |  | 63400 | [5 empty] | DAILY MUD COSTS
SURVEYS |  |  |  | CUM. MUD MIXED |  | 4432 | [5 empty] | CUM. MUD COSTS |  | 76147.78
|  |  |  | CUM. MUD LOSSES |  | 4144 | [5 empty] | AFE COST - C&S |  | 2847416
|  |  |  | CUM. GEL |  | 6000 | [5 empty] | AFE COST - P&A |  | 2588872
|  |  |  | CUM. BARITES |  | 12950 | [5 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 0:30 | Continue with P & A Plug No 4, 1320 - 1260m, 95 sacks of G cement
0:30 | 1:00 | Pull up out of cement & lay out pipe
1:00 | 1:30 | Run P & A Plug No 5, 1255 - 1195m, 95 sacks of G cement
1:30 | 3:30 | Pull up out of cement & lay out pipe
3:30 | 4:00 | Run P & A Plug No 6, 575 - 510m, 110 sacks of G cement
4:00 | 4:30 | Pull up out of cement & lay out pipe
4:30 | 5:30 | Break kelly
5:30 | 8:00 | Lay down pipe
8:00 | 9:30 | Lay down kelly, kelly spinner, swivel & bushings
9:30 | 11:00 | Run in & tag cement at 499m, set 15klbs weight on plug. Pressure test to 750psi for 5 minutes.
11:00 | 13:30 | Lay out pipe
13:30 | 20:00 | Nipple down BOP's, clean mud tanks. Set surface cement plug & weld on cap & well sign
Rig released from Childer's Cove 1 at 20:00hrs for move to Woodside operations
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: |  |  |  |  | MUD CO: | M-I
Childers Cove 1 REPORT #18