## DDR Page 1
DAILY DRILLING REPORT
ESSENTIAL PETROLEUM EXPLORATION Pty Ltd
WELL: |  | EASTWING-1ST |  |  |  |  | DATE: | 2008-06-02 |  | 2008-06-02
PERMIT: |  | PEP 168 |  |  |  |  | REPORT No: | DDR 38
RIG: |  | ADS Rig 6 |  |  |  |  | D.F.S. | 38
DEPTH 2400 Hrs: |  | 2305 |  | OPERATIONS at 0600 Hrs: | Preparing to raise BOP to install Casing slips in wellhead
| TVD | 0 |  | FORMATION: | Eumeralla
| 24 HR PROG.: | TD | LAST CASING: | 5 1/2" | AT | 2293 | SHOE L.O.T.: | 13.3
| HOLE SIZE: | 8.5 | ELEV: | 59 | RT - GL: | 4.3 | MAASP: | 404
FROM | TO | HOURS | OPERATIONS
0-0 | 02.00 | 2 | Layed out the BHA
02.00 | 03.30 | 1.5 | Rigged down excess drilling equipment from the rig floor
03.30 | 04.00 | 0.5 | Retrieved the wear bushing
04.00 | 05.30 | 1.5 | Rigged up for running the 5.5" casing
05.30 | 06.00 | 0.5 | Serviced the rig
06.00 | 06.30 | 0.5 | Held safety meeting on casing running procedures
06.30 | 22.00 | 15.5 | Ran 5.5" casing to 2277m
22.00 | 24.00 | 2 | Washed casing down to 2293m RKB then circulated
HS&E No Incidents reported
`
24
OPERATIONS TO 0600 HRS:
00.00-00.30 Held safety meeting with HOWCO
00.30-03.30 Cemented casing-displaced with water,inhibitor-bumped plug 1800psi held good
03.30-06.00 Cleaned and flushed BOP,prepare to raise BOP to install casing slips
PROGRAMME NEXT 24 HRS: |  |  | Install casing slips-then remove BOP-install tubing spool with "X" bushing (NOT ENERGIZED)
secure wellhead with valve and blind flange w/- needle valve -
WELL COSTS (A$) |  |  | DAILY COST: | 67291 |  | CUMULATIVE: | 3101376
Page 1 of 2

## DDR Page 2
DAILY DRILLING REPORT
ESSENTIAL PETROLEUM EXPLORATION Pty Ltd
WELL: | EASTWING-1ST | [5 empty] | DATE: | 2008-06-02
PERMIT: | PEP 168 | [5 empty] | REPORT No. | DDR-38
RIG: | ADS Rig 6 | [5 empty] | D.F.S. | 38
MUD PROPERTIES |  | ADDITIVES |  | SOLIDS | CONTROL |  | SAFETY/BOP/DRILLS
DENSITY(SG) | 9.30 | Bio- |  | gpm | uf | hrs | ACCIDENT FREE DAYS |  | 340
VISCOSITY(Secs) | 42 | Gel-0 | DESILTER |  |  |  | LAST BOP DRILL |  | 26/5/08
pH | 8.5 | Kcl-0 | DESANDER |  |  |  | LAST FIRE DRILL
PV/YP | 16/17 | CaCo3-0 | CENTRIFUGE 1 |  |  |  | LAST H2S DRILL
GELS 10/10 | 2/8 | Phpa-0 | CENTRIFUGE 2 |  |  |  | LAST BOP TEST
WL API (cc/30min) | 7.2 | Xan-0 |  |  |  |  | BOP TEST DUE |  | 30/5/08
WL HTHP(cc/30min) | 0 | So/Su-0 | SHAKERS | 2 |  |  | FORMATION DATA
CAKE(mm) | 1 | Pac-R-0 | SCREENS | 4/52-4/154 |  |  | DEPTH
SOLIDS % | 5.7 | Caustic0 | PUMPS | 1 | 2 | 3 | TRIP GAS (%)
SAND % | 0.25 | Rod Free-0 | TYPE | SB 700 | NP 600 |  | CONN. GAS (%)
CHLORIDES(mg/l) | 34,000 | Quickseal-0 | STROKE(in) | 16 | 8 |  | B'GRD GAS (%)
KCL % | 2.7 | Citric-0 | LINER(in) | 5.5 x 2.75 | 5.5 |  | PORE PRESS (ppg)
MBT | 12.5 | Salt- 49 | SPM |  | 0 |  | ECD (ppg)
TEMP °C |  | SodaAsh-0 | GPM |  | 0 |  | LITHOLOGY
HOLE VOL(bbl) | 501 | Fracseal-0 | SPP ~ psi |  | 0 |  |  | TIME ANALYSIS
SURF VOL(bbl) | 380 |  | AV-DP(m/min) |  |  |  |  | HRS | CUM.
LOSSES(bbl/hr) |  |  | AV-DC(m/min) |  |  |  | 1. MOVE RIG
MUD Co | RMR |  | SCR - spm |  |  |  | 2. RIG UP |  | 27
MUD TYPE | KCL/PHPA |  | SCR - spm |  |  |  | 3. DRILLING |  | 288
| BIT DATA |  | BHA DETAILS |  | BHA No. |  | 4. TRIP |  | 69
BIT No. | 10RR | 9RR | TOOL |  | OD (in) | Length (m) | 5. WIPER TRIP | 17 | 70.5
SIZE (in) | 8.5 | 8.5 |  |  |  |  | 6. SURVEY |  | 9.5
TYPE | CH04MRS | CH04MRS |  |  |  |  | 7. CIRC./COND | 1 | 19.5
IADC CODE | [6 empty] | 8. HANDLE BHA |  | 41
SERIAL No. | 214054 | 214054 |  |  |  |  | 9. CASE/CEMENT |  | 13
NOZZLES(mm) | 0-0-0 | 0-0-0 |  |  |  |  | 10. WELLHEAD |  | 1.5
DEPTH IN (m) | [6 empty] | 11. BOPS/DIV |  | 31.5
DEPTH OUT (m) | [6 empty] | 12. LOT |  | 1
DRILLED (m. cum) | [6 empty] | 13. CORING
HOURS (cum.) | [6 empty] | 14. LOGGING | 3.5 | 20.5
GRADE | Wiper trip | Wiper trip |  |  |  |  | 15. REAM/WASH | 2.5 | 33.5
AVGE ROP (m/hr) | [6 empty] | 16. FISH/STUCK |  | 94
WOB (mt) | [6 empty] | 17. LOSS CIRC
RPM | [6 empty] | 18. KICK CONTROL
JET VEL (m/sec) |  |  | BHA LENGTH (m) |  |  |  | 19. SIDETRACK |  | 89.5
HHP @ BIT |  |  | BHA WEIGHT (Klbf) |  |  |  | 20. RIG REPAIR |  | 46.5
|  |  | STRING WEIGHT (Klbf) |  |  |  | 21. WELL TEST
SURVEYS: | DEPTH | DEVIATION | AZIMUTH | TVD | COMMENTS |  | 22. WO WEATHER
ST-19 | 2144 | 4 | 353 | 2139 | SS final survey |  | 23. WAIT -WOC |  | 6.5
ST-14 | 1525 | 9.5 | 50 | 1524 | SS |  | 24. ABD./SUSPEND
ST-15 | 1609 | 9.5 | 55 |  | SS |  | 25. RIG SERVICE |  | 6.5
ST-16 | 1762 | ~ | ~ |  | Missrun |  | 26. SLIP/CUT LINE |  | 4
ST-17 | 1896 | 3.75 | 43 |  | SS |  | 27. OTHER recon mud |  | 15.5
ST-18 | 2049 | 5.25 | 12 |  | SS |  | COMPLETION
DRILLING TOOLS | SERIAL No. | CUM. HOURS | DRILLING DATA |  |  |  | TOTAL (HRS) | 24 | 888
|  |  | DRAG - UP (Klbf) | [5 empty] | 816
BICO JAR | DJ001 | 139.5 | DRAG - DOWN (Klbf)
MONEL | K779 | 139.5 | TORQUE-On Bottom (Kft.lb) |  | n/a
USED S STAB | T 2264 | 214 | TORQUE-Off Bottom (Kft.lb) |  | n/a
WEATHER | WEATHER STATE |  | RAINFALL (mm) | TEMP.(°C) | VISIBILITY (km) |  | WIND SPEED(kts) | OTHER
| clear |  |  | 3-15 | clear |  | 0-5 | cool
BULK STOCK | GEL(sx) | BARITE(sx) | CEMENT(sx) | DRILLWATER |  | POT WATER |  | DIESEL FUEL
| 84 | 500 | [5 empty] | 9400
PERSONNEL ON RIG |  |  |  | TRANSPORTATION |  | COMMENTS/REQUIREMENTS
OPERATOR |  | 1 | TRUCKS | LOAD | HOURS
DRILLING CONTRACTOR |  | 18
SERVICE COMPANYS
| Mud Logging Crew | 2 |  |  |  | Mud logger off payroll rigging down as at 06:00hrs
| Mud Engineer | 1 |  |  |  | Mud Engineer leaving site today 3/6/08
| Cementers | 2
Electric Logging Crew
DST Crew
OTHERS
| TOTAL | 24
SUPERVISOR | L.Devattimo |  | ENGINEER | GR | RIG MANAGER |  | S.Kinnearly
Page 2 of 2
Note on F25: Dave Hair: 2.4 gps - - .057 Bstk
Note on E23: Dave Hair: .31 b/stk 5.59gals 97%
Note on B40: Dave Hair: 69m first run
Note on B41: Dave Hair: 10.5 hrs first run