DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 3, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 260 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 182 | 182 |
| CAMERON | 1735 | 1735 |
| HALLIBURTON | 3539 | 3539 |
| SCHLUMBERGER | 2444 | 2444 |
| ISS | 252 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 3, 2007

Supervisor:	Bigby, Brigham

Campbell, Glenn R

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 10.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $233,967 |  |  |
| Total Cost: | $2,193,415 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: | 641.00/ |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Held trip drill. N/u & test casing spool. N/u BOP's. Conduct BCFT & 14 Day BOP Test. Service workboat. Mix KCl/Polymer mud. C/out mud pump liners for production hole interval. C/out TDS saver sub for 4" DP. Conduct rig service. Run wear bushing. L/out 5" DP for setback limit management. |
| Current: | L/out 5" DP. |
| Planned: | P/u 8-1/2" drilling BHA. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 3, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 260 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 182 | 182 |
| CAMERON | 1735 | 1735 |
| HALLIBURTON | 3539 | 3539 |
| SCHLUMBERGER | 2444 | 2444 |
| ISS | 252 | 2357 |

Well: FTA_A12a

Rig/Contractor: 	Rig 175	Report Date: February 3, 2007

Supervisor:	Davis, Brian

Bareswill, JR (Dicky)

Bennett, James

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 22.75 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $179,958 |  |  |
| Total Cost: | $3,715,884 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA A12a |
| --- | --- |
| Management Summary: | Continue rig move from BBMT to FTA. 28% Rig up completed. Expected Rig-up completion date = 23 Feb 07 |
| Current: | Mobilize Rig 175 from BBMT to FTA. |
| Planned: | Mobilize Rig 175 from BBMT to FTA. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 4, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 261 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 183 | 183 |
| CAMERON | 1736 | 1736 |
| HALLIBURTON | 3540 | 3540 |
| SCHLUMBERGER | 2445 | 2445 |
| ISS | 253 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 4, 2007

Supervisor:	Bigby, Brigham

Campbell, Glenn R

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 11.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $233,967 |  |  |
| Total Cost: | $2,193,415 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: | 677.00/ |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Held trip & power choke drills. Complete l/out 5" DP for setback limit management. Pressure test surface casing to 1000 psi - solid. P/u & RIH w/ 8-1/2" drilling BHA. P/u 33 jts of 4" DP on TIH. Tag TOC at 569m. Drill out cement from 569m to 641m. Drill new hole to 646m. Conduct PIT to 12.5 ppg MWE - no leakoff. Drill, steer & survey 8-1/2" production hole from 646m to 677m. |
| Current: | Drill 8-1/2" production hole. |
| Planned: | Continue to drill 8-1/2" production hole. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 4, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 261 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 183 | 183 |
| CAMERON | 1736 | 1736 |
| HALLIBURTON | 3540 | 3540 |
| SCHLUMBERGER | 2445 | 2445 |
| ISS | 253 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 4, 2007

Supervisor:	Davis, Brian

Bareswill, JR (Dicky)

Bennett, James

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 23.75 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $179,958 |  |  |
| Total Cost: | $3,895,842 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Continue rig move from BBMT to FTA. 28% Rig up completed. Expected Rig-up completion date = 23 Feb 07 |
| Current: | Mobilize Rig 175 from BBMT to FTA. |
| Planned: | Mobilize Rig 175 from BBMT to FTA. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 5, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 262 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 184 | 184 |
| CAMERON | 1737 | 1737 |
| HALLIBURTON | 3541 | 3541 |
| SCHLUMBERGER | 2446 | 2446 |
| ISS | 254 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 5, 2007

Supervisor:	Bigby, Brigham

Campbell, Glenn R

Bareswill, JR (Dicky)

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 12.5 | AFE Cost/Days: | $6,507,763 |
| Daily Cost: | $249,661 |  |  |
| Total Cost: | $2,680,506 | Planned MD/TVD: | 2,984.99/ |
| Casing Size: |  | Actual MD/TVD: | 1,180.00/ |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM's. Held pit drills. Drill, steer & survey 8-1/2" production hole from 677m to 1180m. Rig service. |
| Current: | Rig service. |
| Planned: | Continue to drill 8-1/2” production hole. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 5, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 262 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 184 | 184 |
| CAMERON | 1737 | 1737 |
| HALLIBURTON | 3541 | 3541 |
| SCHLUMBERGER | 2446 | 2446 |
| ISS | 254 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 5, 2007

Supervisor:	Davis, Brian

Bareswill, JR (Dicky)

Bennett, James

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 24.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $179,958 |  |  |
| Total Cost: | $4,075,800 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Continue rig move from BBMT to FTA. 35% Rig up completed. Expected Rig-up completion date = 23 Feb 07 |
| Current: | Mobilize Rig 175 from BBMT to FTA. |
| Planned: | Mobilize Rig 175 from BBMT to FTA. |