DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 7, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 292 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 214 | 214 |
| CAMERON | 1767 | 1767 |
| HALLIBURTON | 11 | 3570 |
| SCHLUMBERGER | 2476 | 2476 |
| ISS | 284 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: March 7, 2007

Supervisor:	Smith, Gary G

Campbell, Glenn R

| AFE Number: AFE Number: | L0501H210 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 7.13 | AFE Cost/Days: | $6,614,569 |
| Daily Cost: | $246,846 |  |  |
| Total Cost: | $2,469,585 | Planned MD/TVD: | 2,534.55 / 3,011.30 |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | PTSM's. Held pit & trip drills. RIH with 8-1/2" steerable BHA. Rig service. Precautionary wash & ream last std to bottom. Kickoff well & drill from 549m to 582m. Observed increased PUWT's. Backreamed & conditioned hole. Circulate clean. Drill, steer & survey 8-1/2" production hole from 582m to 749m. |
| Current: | Drill 8-1/2" production hole. |
| Planned: | Continue to drill, steer & survey 8-1/2" production hole. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 7 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 292 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 214 | 214 |
| CAMERON | 1767 | 1767 |
| HALLIBURTON | 11 | 3571 |
| SCHLUMBERGER | 2476 | 2476 |
| ISS | 284 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: March 7 2007

Supervisor:	Steel, George

Moss, Ross

Stead, Cory

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 53.5 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $3,289 |  |  |
| Total Cost: | $9,393,619 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Complete P/U & racking 5½" DP & 5½" HWDP. Open BOP bonnets & inspect BOP body, bonnet sealing area & seals. R/U & commence BOP testing. |
| Current: | Testing BOP's. |
| Planned: | Complete BOP testing. Continue rig up ops. Commision rig. Offload SBM. |