DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS December 12, 2006

| RIG 453 | 207 | 363 |
| --- | --- | --- |
| CAMERON | 1679 | 1679 |
| HALLIBURTON | 3466 | 3466 |
| SCHLUMBERGER | 2408 | 2408 |
| ISDL | 207 | 647 |
| ISS | 195 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: December 12, 2006

Supervisor:	Bennett, James M

Davis, Brian

| AFE Number: | LO501G206 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 41.0 | AFE Cost/Days: | $6,713,761 |
| Daily Cost: | $163,066 |  |  |
| Total Cost: | $6,907,482 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | PTSM & hazard hunts. Service "Far Scandia". Offload barite and 16" casing. Assist Electrician fire and gas shutdown test. Continue to work through DNV commissioning list. Re-instate services & access ways to the rig. Install drill water line. Crane shutdown @ 10:00 Hrs with 40+ knot wind. Unable to continue rig up over conductor #23 or service the work boat due to weather. Continue with scaffolding, housekeeping and general rig up were possible. Crane operational @ 02:30hrs. Boat continue standing off due to sea state. |
| Current: | Wait on weather. Commissioning list. Scaffolding. |
| Planned: | Service boat. Complete commissioning list. General rig up operations. |