LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Loy Yang-2 | REPORT No. : | 14 | DFS: | 13.25 | DATE : | 18-03-2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1443m | LAST DEPTH : | 1443m | 24 HR PROGRESS: | 0m | PTD : | 1443m |
| TOTAL FUEL : | 2,600 | FUEL USAGE : | 1,100 | DAYCOST : $ | 123,450 | CUM. COST : $ | 1,181,172 |
| 0600 OPS : | DST # 3 in progress with Tool shut in for One hour prior to Trip out |
| Next 24 Hrs Op | Trip out ,laying out drill string then run 4-1/2 “ Casing |
| Site Personnel: | Lakes 2Higgins 2 Hunt Energy 15 Hunt Camp 4 Aust DST 2 Total 25 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Run Number | 6 Re-run # 1 |  |  | Drilling |  |  | Density | 8.75 | PPG |
| Size (mm) | 156 |  |  | Tripping |  |  | Viscosity | 35 | Sec |
| Make | Reed |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type | DSX416S-A1 |  |  | Rig repairs |  |  | pH | 9.00 | Strip |
| IADC Code | S-222 |  |  | Testing/tools |  |  | Filter Cake | 1.0 | 32 nd |
| Serial Number | 211343 |  |  | Circulate Sample |  |  | PV / YP | 6 / 13 | Cp/lb/100’ |
| Nozzles (32) | 12-12-12-12 |  |  | Light reaming |  |  | Gels | 3 / 4 / 5 | S/m |
| Depth in (m) | 1164 |  |  | Cementing |  |  | Sand | 0.15 | % Vol |
| Depth out (m) | 1443 |  |  | Slip and Cut line |  |  | Solids | 2.7 | % Vol |
| Total Metres |  |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours |  |  |  | Rig service |  |  | K+ |  | Mg/l |
| WOB (kg) | 4000 |  |  | Rig up BOP |  |  | Chlorides | 5,500 | Mg/l |
| RPM | 100 |  |  | Logging |  |  | PHPA |  |  |
| Condition | 10% worn |  |  | DST |  |  | KCL | 1.10 | % by vol |
| Impact Force | 206. |  |  | Wait On Cement |  |  | Daily Cost $ | 2,443 |
| Jet Velocity | 183ft/sec |  |  | Test BOPs |  |  | Cum Cost $ | 35,759 |
| BHA: |  |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From |  | Operation |  |  | ° at |  | m |  | Type | Amount |
| 00:00 | 06:00 | Continued to run log # 3 |  |  | ° at |  | m |  | Barazan-D plus |  |
| 06:00 | 10:30 | Wiper tripped in hole to bottom at 1443m |  |  | ° at |  | m |  | Dextrid LTE |  |
| 10:30 | 11:30 | Circulated |  |  | ° at |  | m |  | Baracide / Pac-L |  |
| 11:30 | 15:00 | Tripped out for DST |  |  | ° at |  | m |  | N-VIS Plus |  |
| 15:00 | 17:00 | Made up DST # 3 tools |  |  | ° at |  | m |  | KCL Tech |  |
| 17:00 | 17:30 | Held safety meeting on incident to DST helper |  |  | ° at |  | m |  | Baracor 129 |  |
| 17:30 | 21:00 | Tripped in hole to bottom at 1443m no fill |  |  | ° at |  | m |  | Potassium Hydrox |  |
| 21:00 | 22:00 | Rigged up surface equipment then held safety meeting |  |  |  |  |
| 22:00 | 22:30 | Opened tool and flowed well |  | PUMP 1 |  | PUMP 2 |
| 22:30 | 24:00 | Flowed well and observed influx into the pipe string |  | Liner | 140 | mm |  | Liner |  | mm |
|  |  |  |  | Pressure | 7,700 | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP | 64.8 | f/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 100.4 | f/in |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 45 |  | SPM |  |
|  |  |  |  | GPM | 252 |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton | 198 |  | Size | 177.80 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 38.69 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | N-80 |  |
|  |  | JSA F.E.L operations |  | % |  |  |  | Connection | Buttress |  |
|  |  | JSA Rig equipment safety and maintenance |  | % |  |  |  | Joints | 18 |  |
|  |  |  |  | % |  |  |  | Length | 216.00 | m |
| Days since | LTA | 567 |  | Halliburton cost | $ 31,212 |  | Shoe | 220m from RKB | m |

,66