LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Loyang-2 | REPORT No. : | 4 | DFS: | 3.25 | DATE : | 8-03-2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 450.00m | LAST DEPTH : | 423.6m | 24 HR PROGRESS: | 26.4m | PTD : | 1250m |
| TOTAL FUEL : | 9050 | FUEL USAGE : | 1050 | DAYCOST : $ | 30,243 | CUM. COST : $ | 696,883 |
| 0600 OPS : | Reverse circulating formation fluid from DST # 1 to surface |
| Next 24 Hrs Op | Trip out with DST tools- Cut core #-2 |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | Core Head # 1 | 3 Re-Run # 1 |  | Drilling | 4.00 |  | Density | 8.50 | S.G. |
| Size (mm) | 152.4 | 156 |  | Tripping | 9.50 |  | Viscosity | 48 | Sec |
| Make | Corpro | Reed |  | Surveys |  |  | Water Loss | 7.1 | Cc |
| Type | PDC | DSX 206AIF+GW |  | Rig repairs |  |  | pH | 9.0 | Strip |
| IADC Code | Claw | S-222 |  | Testing/tools |  |  | Filter Cake | 1.0 | 32 nd |
| Serial Number | CP-O2 | 211343 |  | Circulate Sample | 0.50 |  | PV / YP | 10 / 15 | Cp/lb/100’ |
| Nozzles (32) |  | 12-12-12-12 |  | Light reaming | 1.00 |  | Gels | 5 / 6/ 8 | S/m |
| Depth in (m) | 415 | 423.6 |  | Cementing |  |  | Sand | 0.20 | % Vol |
| Depth out (m) | 423.6 | 450 |  | Coring | 5.50 |  | Solids | 0.70 | % Vol |
| Total Metres | 8.6 | 27.6 |  | Circulate & Condition | 1.00 |  | Oil |  | % Vol |
| Hours | 3.5 | 4.0 |  | Rig Service |  |  | K+ |  | Mg/l |
| WOB (kg) | 2-6 | 2000kg |  | Rig up BOP |  |  | Chlorides | 6,500 | Mg/l |
| RPM | 60-120 | 110 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | Good | New |  | DST | 2.50 |  | KCL | 1.30 % |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 2,475 |
| Jet Velocity |  |  |  | Test BOPs |  |  | Cum Cost $ | 15,148 |
| B.H.A.: |  |
|  | # 3 Bit-Bit sub-with totco ring -2 drill collars-stabilizer-8 drill collars-Jars 2 drill collars |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 03:30 | Cut core # 1 from 415m to 423.6m |  |  | ° at |  | m |  | Barazan-D Plus | 1 |
| 03:30 | 04:00 | Circulated |  |  | ° at |  | m |  | Dextrid LTE | 4 |
| 04:00 | 05:30 | Tripped out with Core |  |  | ° at |  | m |  | PAC-L | 2 |
| 05:30 | 07:00 | Recovered core ( 2.00 metres ) |  |  | ° at |  | m |  | N-VIS Plus | 5 |
| 07:00 | 10:30 | Tripped in hole with 156mm Bit to 401m |  |  | ° at |  | m |  | KCL Tech | 7 |
| 10:30 | 11:00 | Washed down from 401m to 415m |  |  | ° at |  | m |  | Baracor 129 | 2 |
| 11:00 | 12:00 | Light reamed core rathole from 415m to 423.6m |  |  | ° at |  | m |  | Potassium Hydrox | 2 |
| 12:00 | 16:00 | Drilled 156mm hole from 423.6m to 450m |  |  |  |  |
| 16:00 | 16:30 | Circulated bottoms up sample |  | PUMP 1 |  | PUMP 2 |
| 16:30 | 18:00 | Tripped out |  | Liner | 140 | mm |  | Liner |  | mm |
| 18:00 | 21:30 | Picked up DST tools then tripped in hole |  | Pressure | 2,800 | kPa |  | Pressure |  | KPa |
| 21:30 | 22:30 | Rigged up surface equipment and tested lines |  | A.V. DP | 64.8 | f/min |  | A.V. DP |  | m/min |
| 22:30 | 24:00 | Set packer at 440m then opened tool and flowed well |  | A.V. DC | 117 | f/in |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 42 |  | SPM |  |
|  |  | Ran DST tools with no water cushion |  | GPM | 236 |  | GPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton | 198 |  | Size | 177.80 | mm |
|  |  |  |  | Class Bulk |  |  | Weight | 38.69 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | N-80 |  |
|  |  | JSA Held safety meeting prior to DST |  | % |  |  |  | Connection | Buttress |  |
|  |  | JSA Racking back drill collars |  | % |  |  |  | Joints | 18 |  |
|  |  |  |  | % |  |  |  | Length | 216.00 | m |
| Days since | LTA | 559 |  | Halliburton cost | $ 31,212 |  | Shoe | 220m from RKB | m |

,66