LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 41 | DFS: | 41 | DATE : | 26-11-09 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 2,500 | LAST DEPTH : | 2,500 | 24 HR PROGRESS: |  | PTD : | Total Depth |
| TOTAL FUEL : | 3,500 | FUEL USAGE : | 1,000 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Slipped block line-layed out drill collars-cleared rig floor-changed rams to 4½"-rigging up for Casing at 06.00hrs |
| Next 24 Hrs Op | Run 211 jnts of Casing –cement same-land Casing in Wellhead Spool |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES @ 22.30 |
| --- | --- | --- | --- | --- |
| j Bit Number | 7 RR# 6 |  |  | Drilling |  |  | Density | 1.188 | S.G. |
| Size (mm) | 156 |  |  | Tripping | 18.50 |  | Viscosity | 41 | Sec |
| Make | Reed |  |  | Downtime ( Float ) |  |  | Water Loss | 32 | Cc |
| Type | R22AP |  |  | Wireline logging |  |  | pH | 7.5 | Strip |
| IADC Code | 5-1-7 |  |  | Testing/tools |  |  | Filter Cake | 2 | 32 nd |
| Serial Number | KD1019 |  |  | Circulate Sample |  |  | PV / YP | 8 / 9 | Cp/lb/100’ |
| Nozzles (32) | 14-14-14 |  |  | Casing |  |  | Gels | 2 / 3 | S/m |
| Depth in (m) |  |  |  | Cementing |  |  | Sand | 0.25 | % Vol |
| Depth out (m) |  |  |  | Drill stem testing |  |  | Solids | 9.9 | % Vol |
| Total Metres | Wiper trip |  |  | Circulate & Condition | 5.00 |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service/slip & cut | 0.50 |  | K+ | 7,875 | Mg/l |
| WOB (kg) |  |  |  | Rig up/ d own bop |  |  | Chlorides | 15,000 | Mg/l |
| RPM |  |  |  | Drill out Cmt |  |  | K+ | 10,500 |  |
| Condition |  |  |  | Reaming |  |  | KCL | 2.0 | % |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 675 |
| Jet Velocity |  |  |  | Test BOPs |  |  | Cum Cost $ | 92,290 |
| B.H.A.: | 156mm Bit-Bit Sub-14 x 4¾" Drill Collars- |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 00.30 | Continued to trip in hole 156mm Bit ( Wiper trip ) |  |  | ° at |  | m |  | AMC Pac L |  |
| 00.30 | 01.00 | Circulated at 1526m Mud wt in 9.7 Mud wt out 9.5ppg |  |  | ° at |  | m |  | AMC Pac R |  |
| 01.00 | 02.00 | Continued trip in hole to 1909m |  |  | ° at |  | m |  | Caustic | 1 |
| 02.00 | 02.30 | Circulated Mud wt in 9.6 Mud wt out 10.3ppg |  |  | ° at |  | m |  | Xan Bore |  |
| 02.30 | 03.00 | Continued trip in hole to 2195m |  |  | ° at |  | m |  | Bayrtes | 50 |
| 03.00 | 04.00 | Circulated Mud wt in 9.6 Mud wt out 9.4ppg |  |  | ° at |  | m |  | Potassium Chloride |  |
| 04.00 | 04.30 | Continued trip in hole to 2253m ( Resistance ) |  |  | ° at |  | m |  | AMC Biocide G | 1 |
| 04.30 | 05.00 | Picked up Kelly washed down to 2271m |  |  |  |  |
| 05.00 | 06.30 | Layed out 20 jnts pipe from derrick |  | PUMP 1 Duplex |  | PUMP 2 Triplex |
| 06.30 | 10.00 | Washed down to 2500m |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 10.00 | 12.00 | Circulated and conditioned mud to 9.9ppg and 41 vis |  | Pressure |  | kPa |  | Pressure |  | KPa |
| 12.00 | 12.30 | Slugged pipe |  | A.V. DP |  | f/min |  | A.V. DP |  | Ft/min |
| 12.30 | 19.00 | Layed out drill string to 952m |  | A.V. DC |  | f/min |  | A.V. DC |  | Ft//mn |
| 19.00 | 20.30 | Picked up Kelly broke out connections |  | SPM |  |  | SPM |  |
| 20.30 | 23.30 | Continued to lay out drill string |  | GPM |  |  | GPM |  |
| 23.30 | 24.00 | Slipped block line |  |  |  |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 7" | inch |
|  |  | Hunt 19 camp 4 Schlumberger stby |  | Class Bulk |  |  | Weight | 26 | ppf |
|  |  | Lakes 3 |  | % |  |  |  | Grade | K-55 |  |
|  |  | Mud logger 2 |  | % |  |  |  | Connection | BTC |  |
|  |  | Farley Riggs 2 left site |  | % |  |  |  | Joints | 117 |  |
|  |  | RMN 1 |  | % |  |  |  | Length | RT-Brd Hd 5.0 | m |
| Days since | LTA | 467 |  | Av. Wt |  |  | Shoe | 1376m from RKB | m |

,66