## Report
| DAILY DRILLING REPORT | [12 empty] | 2005-09-10
26
WELL | Peterborough 01ST1 |  |  |  | 24:00 DEPTH | 2070 |  |  | 24 HR PROG | 0 |  |  | CUM. COSTS | 3049465.09
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION |  | C Dann / Q Cahill | C Dann / Q Cahill | PTD | 2075 |  |  | DAILY COSTS | 19805.42
OP's TO 06:00 |  | Rig down
REMARKS: |  | Rig release at 9:00 hrs | [9 empty] | PERSONNEL ON SITE: |  |  | 28
LAST CASING |  | 9.625 | SET AT | 495.55 | LOT | 16.8036 | MAASP |  |  |  | BOP TEST | 2005-08-19 |  | TEST DUE | DUE
44 |  | SAFETY | 1. Rig 11 battery incident | [9 empty] | WEATHER AM | Cool / Showers
|  |  | 2. Rig 11 battery incident | [9 empty] | PM | Cool / Showers
BIT INFORMATION | [8 empty] | MUD PROPERTIES |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0 | JET V(fps) |  | TOOL |  |  | LENGTH |  | Time |  |  | Casing |  |  | 9
RPM | 0 | H S I | [6 empty] | Depth (m) |  |  | Cementing |  |  | 5.5
BIT NUMBER |  |  | 0 | [5 empty] | Temp (° C) |  |  | Circ & Condition |  |  | 17.5
Size (in) | [8 empty] | Mud Type |  |  | Coring |  |  | 0
Make | [8 empty] | Density (ppg) | 0 |  | D/O Cement |  |  | 1.5
Type | [8 empty] | ECD (ppg) |  |  | Drilling |  |  | 229
IADC Code | [8 empty] | Viscosity (sec) |  |  | Handle BHA |  |  | 26.5
Serial Number | [8 empty] | PV / YP (cp/lb) |  |  | LOT / FIT |  |  | 1
T.F.A.( ") | [8 empty] | Gells (s/m) |  |  | N/U & Test BOP's |  |  | 19
Depth In (m) | [8 empty] | API Filt. (cc) |  |  | P & A |  | 9 | 46.5
Depth Out (m) | [8 empty] | Cake (/32") |  |  | Repairs |  |  | 9.5
Total Meters | [8 empty] | Solids (% Vol) |  |  | Rig Move |  |  | 20.5
Hours | [8 empty] | Sand (% Vol) |  |  | Rig Service |  |  | 6
ROP | [8 empty] | MBT |  |  | Safety |  |  | 1
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 0 |  | pH (strip) |  |  | Survey |  |  | 14.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 0 |  | Chlorides (mg/l) |  |  | Tight hole / Fishing |  |  | 40
CIRC. RATE (gpm) |  | 0 |  | STRING WT (kLb) |  |  |  |  | KCL (% ) |  |  | Tripping |  |  | 109
AV - DP (fpm) |  | 0 |  | HOOK LOAD (kLb) |  |  |  |  | PHPA (ppb) |  |  | Wait on Cement |  |  | 11.5
AV - DC (fpm) |  | 0 |  | WT BELOW JARS (kLb) |  |  | 0 |  | ALC - 50 (K) |  |  | Wash / Ream |  |  | 9.5
SPP (psi) |  |  |  | DRAG UP (kLb) |  |  |  |  | Circ. Vol. (Bbl) |  |  | Well Control |  |  | 0
SPP (calculated) |  |  |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) | [7 empty] | Wellhead |  |  | 4.5
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) | [7 empty] | Wiper Trip |  |  | 5
RATE | 0 | RATE | 0 | ENVIRONMENTAL DATA | [7 empty] | Wireline |  |  | 14.5
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 12900 | [5 empty] | Other |  |  | 8
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 700 | [5 empty] | TOTALS |  | 9 | 609
|  |  |  | CUM. FUEL USED |  | 83000 | [5 empty] | DAILY MUD COSTS
SURVEYS |  |  |  | CUM. MUD MIXED |  | 3487 | [5 empty] | CUM. MUD COSTS |  | 74007.67
|  |  |  | CUM. MUD LOSSES |  | 3144 | [5 empty] | AFE COST - C&S |  | 2687024
|  |  |  | CUM. GEL |  | 7200 | [5 empty] | AFE COST - P&A |  | 2475824
|  |  |  | CUM. BARITES |  | 17000 | [5 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 1:00 | Continue to lay out drill pipe (28 joints)
1:00 | 2:00 | Flush BOP and Choke manifold. Clean floor and layout excess drilling equipment from floor
2:00 | 3:30 | Lay out kelly and kelly sub
3:30 | 4:30 | Layout bell nipple and flow line
4:30 | 8:30 | Nipple down BOP and choke line manifold
8:30 | 9:00 | Remove A section from 9 5/8" casing. Rig released at 09:00 hours
| SUPERVISOR: | C Dann / Q Cahill |  |  |  |  | GEOLOGIST: |  |  |  |  | MUD CO: | M-I
Peterborough 01ST1 REPORT #26