## Report
| DAILY DRILLING REPORT | [13 empty] | 2005-08-20
5
WELL | Peterborough 01 |  |  |  | 24:00 DEPTH | 704 |  |  | 24 HR PROG | 205 |  |  |  | CUM. COSTS | 1587988.17
RIG | Century Resources Ltd # 7 |  |  |  | FORMATION | Mepunga | S.Porter / B.Webb | S.Porter / B.Webb | PTD | 2075 |  |  |  | DAILY COSTS | 73657.85
OP's TO 06:00 |  | Continue to drill 8 1/2" hole from 704m to 853m
REMARKS: |  | FIT 700psi, 16.8ppg EMW. Drill ahead to 704m midnight depth. | [10 empty] | PERSONNEL ON SITE: |  |  | 33
LAST CASING |  | 9.625 | SET AT | 495.55 | LOT | 16.8036 | MAASP |  | 693.5458 |  |  | BOP TEST | 2005-08-19 |  | TEST DUE | 2005-09-09
23 |  | SAFETY | 1. Nipple up Bops and pressure testing. Working at heights, JSA's. | [10 empty] | WEATHER AM | Overcast
|  |  | 2. Working at heights. Ask questions if unsure. Pre plan . | [10 empty] | PM | Overcast
BIT INFORMATION |  |  |  | 2 |  |  |  |  | MUD PROPERTIES |  |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0-8 | JET V(fps) | 256.323 | TOOL |  |  | LENGTH |  | Time | 22:00 |  |  | Casing |  |  | 9
RPM | 80-130 | H S I | 3.2097 | PDC Bit |  |  | 0.3 |  | Depth (m) | 685 |  |  | Cementing |  |  | 2
BIT NUMBER |  | 2 | 0 | PowerDrive 675 |  |  | 4 |  | Temp (° C) | 35 |  |  | Circ & Condition |  |  | 3
Size (in) |  | 8.5 |  | Float Sub |  |  | 0.48 |  | Mud Type | KCL/Poly/Phpa |  |  | Coring |  |  | 0
Make |  | Smith |  | 8-1/4" String Stab |  |  | 1.81 |  | Density (ppg) | 8.6 |  |  | D/O Cement |  | 1.5 | 1.5
Type |  | M 90 |  | x/o |  |  | 0.51 |  | ECD (ppg) | 9.039 |  |  | Drilling |  | 11 | 35
IADC Code |  | M223 |  | Anderdrift |  |  | 3 |  | Viscosity (sec) | 51 |  |  | Handle BHA |  | 2.5 | 2.5
Serial Number |  | JT6937 |  | 14 x 6-1/2" DC's |  |  | 129 |  | PV / YP (cp/lb) | 12 / 17 |  |  | LOT / FIT |  | 1 | 1
T.F.A.( ") |  | 0.77313 |  | Drilling Jars |  |  | 9.77 |  | Gells (s/m) | 5 / 7 |  |  | N/U & Test BOP's |  | 4 | 19
Depth In (m) |  | 499 |  | 2 x 6-1/2" DC's |  |  | 18.26 |  | API Filt. (cc) | 9 |  |  | P & A |  |  | 0
Depth Out (m) |  | IN |  | 4 x 4-1/2" HWDP |  |  | 37.36 |  | Cake (/32") | 0.5 |  |  | Repairs |  |  | 3
Total Meters |  | 205 | [6 empty] | Solids (% Vol) | 0.2 |  |  | Rig Move |  |  | 20.5
Hours |  | 11 | [6 empty] | Sand (% Vol) |  |  |  | Rig Service |  |  | 1
ROP |  | 18.6364 | [6 empty] | MBT |  |  |  | Safety |  |  | 0
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 204.49 |  | pH (strip) | 9.5 |  |  | Survey |  |  | 2
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 43.9126 |  | Chlorides (mg/l) | 20000 |  |  | Tight hole / Fishing |  |  | 0
CIRC. RATE (gpm) |  | 617.6216 |  | STRING WT (kLb) |  |  | 70.7449 |  | KCL (% ) | 4.5 |  |  | Tripping |  | 2.5 | 11
AV - DP (fpm) |  | 291.1136 |  | HOOK LOAD (kLb) |  |  | 85 |  | PHPA (ppb) |  |  |  | Wait on Cement |  |  | 5
AV - DC (fpm) |  | 456.1328 |  | WT BELOW JARS (kLb) |  |  | 33.5096 |  | ALC - 50 (K) |  |  |  | Wash / Ream |  |  | 0
SPP (psi) |  | 1250 |  | DRAG UP (kLb) |  |  | 2 |  | Circ. Vol. (Bbl) | 480 |  |  | Well Control |  |  | 0
SPP (calculated) |  | 1060 |  | DRAG DOWN (kLb) |  |  | 2 |  | CHEMICAL USAGE |  |  |  | Well Test |  |  | 0
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) |  |  | 2000 |  | Duo-Tec |  | 7 |  | Wellhead |  | 1.5 | 4.5
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) |  |  |  |  | Polypac UL |  | 4 |  | Wiper Trip |  |  | 0
RATE | 102 | RATE | 102 | ENVIRONMENTAL DATA |  |  |  |  | Sod Sulphite |  | 2 |  | Wireline |  |  | 0
LINER | 6 | LINER | 6 | FUEL ON SITE |  | 23500 |  |  | Pot chloride |  | 42 |  | Other |  |  | 0
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 2300 |  |  | Polyplus |  | 4 |  | TOTALS |  | 24 | 120
SCR: 200 @ 60 |  | SCR: 200 @ 60 |  | CUM. FUEL USED |  | 11900 | [6 empty] | DAILY MUD COSTS |  | 3832.85
SURVEYS |  |  |  | CUM. MUD MIXED |  | 971 | [6 empty] | CUM. MUD COSTS |  | 15840.17
0° at 505m |  | 0° at 685m |  | CUM. MUD LOSSES |  | 877 | [6 empty] | AFE COST - C&S |  | 2687024
2° at 657m |  | 0° at 694m |  | CUM. GEL |  | 5775 | [6 empty] | AFE COST - P&A |  | 2475824
2° at 666m |  |  |  | CUM. BARITES |  | 0 | [6 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 4:00 | Complete Bop testing. Test Choke and kill manifold, Test Surface equip>kelly, stab valves, standpipe, mud pump isolation valves.
4:00 | 5:30 | Install wear bushing and lay out test plug/ running tool.
5:30 | 8:00 | Make up 8 1/2" BHA and test Power drive. Cont with BHA picking up Anderdrift and drilling jars.
8:00 | 10:30 | RIH and tag cmt top at 477m
10:30 | 12:00 | Drill cement float and shoe equipment and clean out rat hole to 499m, make 3 m of new hole to 502m.
12:00 | 13:00 | Circulate hole clean and perform an FIT. 700psi 16.8 EMW
13:00 | 24:00 | Drill 8 1/2" hole from 502m to 704m, take Anderdrift surveys to check inclination
| SUPERVISOR: | S.Porter / B.Webb |  |  |  |  | GEOLOGIST: | J. Hobday |  |  |  |  | MUD CO: | M-I
Peterborough 01 REPORT #5