DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 29, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 303 | 363 |
| --- | --- | --- |
| CAMERON | 5556 | 5587 |
| HALLIBURTON | 3378 | 3377 |
| SCHLUMBERGER | 2158 | 24 |
| ISDL | 303 | 647 |
| ISS | 91 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 29, 2006

Supervisor:	Basset, Anthony A

Steel, George A

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 2.9 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $746,661 |  |  |
| Total Cost: | $3,774,284 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2544.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | Complete RIH 3½" tandem completion. Correlate packers on depth with GR/CCL. Space out compl & land, EOT-2446.98m. Run N-test tool, set & test packers, OK. Test TR-SSSV, OK. R/d w/line, set BPV. N/down BOP. |
| Current: | N/down 13-5/8" BOP. |
| Planned: | N/up tree, r/u w/line, open SSD, set sand control nipple, R/D. |