DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS October 5, 2006

| RIG 453 | 140 | 363 |
| --- | --- | --- |
| CAMERON | 1615 | 1615 |
| HALLIBURTON | 3403 | 3403 |
| SCHLUMBERGER | 2344 | 2344 |
| ISDL | 140 | 647 |
| ISS | 129 | 2345 |

Well: WKF_W23

Rig/Contractor: 	Rig 453	Report Date: October 5, 2006

Supervisor:	Campbell, Glenn R.

Steel, George A.

| AFE Number: | 40000460 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 2.0 | AFE Cost/Days: | $1,278,800 |
| Daily Cost: | $ 185,614 |  |  |
| Total Cost: | $ 366,560 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W23 |
| --- | --- |
| Management Summary: | R/up Wireline BOP's. RIH & retrieve SSSV from 455m. Set packoff in SSSV nipple. Pressure test RN plug - crude evident when bleeding down. Pull packoff, attempt to open SSD @ 2546m. Unsuccessful. Pull GLV from 1634m. Forward circulate well to effluent line with ISW. |
| Current: | Circulating well to ISW. |
| Planned: | Set DGLV, set BPV, n/down tree, n/up BOP. |