LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 15 | DFS: | 15 | DATE : | 19 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1449m | LAST DEPTH : | 1385m | 24 HR PROGRESS : | 64m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 36,398 | CUM. COST : $ | 944,841 |
| 0600 OPS : | POH. |
| Next 24 hr OPS: | Make up DST tools. RIH. DST#1 |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 3 |  |  | Drilling | 8.5 |  | Density | 1.14 | S.G. |
| Size (mm) | 216 |  |  | Tripping | 6.0 |  | Viscosity | 37 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type | XSC1S |  |  | Reaming/work tight hole | 2.0 |  | pH | 9.0 | Strip |
| IADC Code | 1.1.7 |  |  | Testing |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10394939 |  |  | Circulate Sample |  |  | PV / YP | 9/12 | Cp/lb/100’ |
| Nozzles (32) | 3x12 |  |  | Casing |  |  | Gels | ½ | S/m |
| Depth in (m) | 1385 |  |  | Cementing |  |  | Sand | Tr | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 4.6 | % Vol |
| Total Metres | 64 |  |  | Circulate & Condition | 2.5 |  | Oil |  | % Vol |
| Hours | 8.5 |  |  | Rig Service/slip & cut |  |  | K+ | 24,318 | Mg/l |
| WOB (kg) | 10,000 |  |  | Test BOP's | 0.5 |  | Chlorides | 25,000 | Mg/l |
| RPM | 90 |  |  | Repairs | 3.0 |  | PHPA | 1.35 |  |
| Condition | IN |  |  | Drill Out | 1.5 |  | ALC - 50 |  |  |
| Impact Force | 7.39 |  |  | Wait On Cement |  |  | Daily Cost $ | 6,794 |
| Jet Velocity | 88.5 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 68,209 |
| B.H.A.: | Bit, bit sub, 2x6-1/2” DC’s, stabilizer, XO, 16x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0300 | RIH. Tag cement at 814m. |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0300 | 0600 | Rig repair. Standpipe leaking during BOP test. |  |  | ° at |  | m |  | Sodium Sulphite | 4 |
| 0600 | 0630 | Test pipe rams and annular. |  |  | ° at |  | m |  | Barite | 232 |
| 0630 | 0700 | Drill out DV tool. At 817m. |  |  | ° at |  | m |  | Drillzan | 5 |
| 0700 | 0900 | RIH. Tag cement at 1342m |  |  | ° at |  | m |  | KCl Tech | 109 |
| 0900 | 1000 | Drill out plugs, shoe track and rathole to 1385m |  |  | ° at |  | m |  | PHPA/Biocide | 6/0 |
| 1000 | 1130 | Drill 216mm hole from 1385m to 1391m |  |  | ° at |  | m |  | Caustic Soda |  |
| 1130 | 1330 | Ream tight hole. Raise MW to 1.12 |  |  |  |  |
| 1330 | 2030 | Drill from 1391m to 1449m. Minor tight hole on |  | PUMP 1 |  | PUMP 2 |
|  |  | Connections. Raise MW to 1.14. |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 2030 | 2130 | Circulate hole clean. |  | Pressure | 7000 | kPa |  | Pressure |  | kPa |
| 2130 | 2230 | Make wiper trip to shoe. |  | A.V. DP | 43 | m/min |  | A.V. DP |  | m/min |
| 2230 | 2400 | Circulate hole clean. Condition mud. |  | A.V. DC | 74 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 54 |  | SPM |  |
|  |  |  |  | LPM | 1136 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 800 |  | Size | 244 | mm |
|  |  |  |  | Class | A |  | Weight | 53.6 | kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 115 |  |
|  |  |  |  | % |  |  |  | Length | 1364 | m |
|  |  |  |  | Av. Wt | 15.6ppg |  | Shoe | 1366 | m |

,66