LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 18 | DFS: | 18 | DATE : | 22 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1537m | LAST DEPTH : | 1449m | 24 HR PROGRESS : | 88m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 42,345 | CUM. COST : $ | 1,055,594 |
| 0600 OPS : | Drilling 216mm hole at 1592m |
| Next 24 hr OPS: | Wiper trip to shoe. Drill ahead. |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 5 |  |  | Drilling | 13.0 |  | Density | 1.22 | S.G. |
| Size (mm) | 216 |  |  | Tripping | 3.0 |  | Viscosity | 44 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type | XSC1S |  |  | Reaming/work tight hole | 8.0 |  | pH | 9.0 | Strip |
| IADC Code | 1.1.7 |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 748179 |  |  | Circulate Sample |  |  | PV / YP | 11/14 | Cp/lb/100’ |
| Nozzles (32) | 3x12 |  |  | Casing |  |  | Gels | 2/4 | S/m |
| Depth in (m) | 1449 |  |  | Cementing |  |  | Sand | 0.5 | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 7.2 | % Vol |
| Total Metres | 88 |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 13 |  |  | Rig Service/slip & cut |  |  | K+ | 22,976 | Mg/l |
| WOB (kg) | 12,000 |  |  | Test BOP's |  |  | Chlorides | 24,500 | Mg/l |
| RPM | 85 |  |  | Repairs |  |  | PHPA | 1.35 |  |
| Condition | IN |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force | 7.39 |  |  | Wait On Cement |  |  | Daily Cost $ | 7,050 |
| Jet Velocity | 88.5 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 75,580 |
| B.H.A.: | Bit, bit sub, 2x6-1/2” DC’s, stabilizer, XO, 16x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0300 | RIH to 1379. Hole tight. |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0300 | 0730 | Ream from 1379m to 1449m. Raise MW to 1.17. |  |  | ° at |  | m |  | Sodium Sulphite | 4 |
| 0730 | 1030 | Drill 216mm hole from 1449m to 1458m. |  |  | ° at |  | m |  | Barite | 494 |
| 1030 | 1300 | Ream tight connection 1449m to 1458m. |  |  | ° at |  | m |  | Drillzan | 4 |
|  |  | Raise MW to 1.19 |  |  | ° at |  | m |  | KCl Tech | 42 |
| 1300 | 1400 | Drill from 1458m to 1467m. |  |  | ° at |  | m |  | PHPA/Biocide | 3 |
| 1400 | 1500 | Ream tight connection from 1458m to 1467m. |  |  | ° at |  | m |  | Caustic Soda | 2 |
|  |  | Raise MW to 1.21. |  |  |  |  |
| 1500 | 2400 | Drill from 1467m to 1537m. |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 7600 | kPa |  | Pressure |  | kPa |
|  |  |  |  | A.V. DP | 43 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 74 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 54 |  | SPM |  |
|  |  |  |  | LPM | 1136 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 800 |  | Size | 244 | mm |
|  |  |  |  | Class | A |  | Weight | 53.6 | kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 115 |  |
|  |  |  |  | % |  |  |  | Length | 1364 | m |
|  |  |  |  | Av. Wt | 15.6ppg |  | Shoe | 1366 | m |

,66