LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 19 | DFS: | 19 | DATE : | 23 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1710m | LAST DEPTH : | 1537m | 24 HR PROGRESS : | 173m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 37,368 | CUM. COST : $ | 1,092,962 |
| 0600 OPS : | Drill ing at 1731m |
| Next 24 hr OPS: | Drill to 1800m TD. Wiper trip prior to logs. |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 5 |  |  | Drilling | 21.0 |  | Density | 1.22 | S.G. |
| Size (mm) | 216 |  |  | Tripping | 1.0 |  | Viscosity | 47 | Sec |
| Make | Security |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type | XSC1S |  |  | Reaming/work tight hole | 1.0 |  | pH | 9.0 | Strip |
| IADC Code | 1.1.7 |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 748179 |  |  | Circulate Sample |  |  | PV / YP | 15/19 | Cp/lb/100’ |
| Nozzles (32) | 3x12 |  |  | Casing |  |  | Gels | 3/6 | S/m |
| Depth in (m) | 1449 |  |  | Cementing |  |  | Sand | 0.5 | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids | 8.1 | % Vol |
| Total Metres | 261 |  |  | Circulate & Condition | 1.0 |  | Oil |  | % Vol |
| Hours | 34 |  |  | Rig Service/slip & cut |  |  | K+ | 21,616 | Mg/l |
| WOB (kg) | 12,000 |  |  | Test BOP's |  |  | Chlorides | 22,000 | Mg/l |
| RPM | 85 |  |  | Repairs |  |  | PHPA | 1.6 |  |
| Condition | IN |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force | 7.39 |  |  | Wait On Cement |  |  | Daily Cost $ | 3,473 |
| Jet Velocity | 88.5 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 79,053 |
| B.H.A.: | Bit, bit sub, 2x6-1/2” DC’s, stabilizer, XO, 16x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0730 | Drill 216mm hole from 1537m to 1609m. |  |  | ° at |  | m |  | AMC PAC-R | 2 |
| 0730 | 0830 | Circulate hole clean |  |  | ° at |  | m |  | Sodium Sulphite | 3 |
| 0830 | 0930 | Wiper trip to shoe. RIH. Bridge at 1569m |  |  | ° at |  | m |  | Barite | 20 |
| 0930 | 1030 | Ream from 1569m to 1609m |  |  | ° at |  | m |  | Drillzan | 3 |
| 1030 | 2400 | Drill from 1609m to 1710m |  |  | ° at |  | m |  | KCl Tech | 36 |
|  |  |  |  |  | ° at |  | m |  | PHPA/Soda Ash | 6/4 |
|  |  |  |  |  | ° at |  | m |  | Caustic Soda | 3 |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 7600 | kPa |  | Pressure |  | kPa |
|  |  |  |  | A.V. DP | 43 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 74 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 54 |  | SPM |  |
|  |  |  |  | LPM | 1136 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 800 |  | Size | 244 | mm |
|  |  |  |  | Class | A |  | Weight | 53.6 | kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 115 |  |
|  |  |  |  | % |  |  |  | Length | 1364 | m |
|  |  |  |  | Av. Wt | 15.6ppg |  | Shoe | 1366 | m |

,66