LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 20 | DFS: | 20 | DATE : | 24 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1775m | LAST DEPTH : | 1710m | 24 HR PROGRESS : | 65m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 26,574 | CUM. COST : $ | 1,119,536 |
| 0600 OPS : | Logging |
| Next 24 hr OPS: | Complete logging. Wiper trip. Run 178mm liner |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 5 |  |  | Drilling | 14.0 |  | Density | 1.22 | S.G. |
| Size (mm) | 216 |  |  | Tripping | 7.5 |  | Viscosity | 49 | Sec |
| Make | Security |  |  | Surveys | 0.5 |  | Water Loss | 6.5 | Cc |
| Type | XSC1S |  |  | Reaming/work tight hole |  |  | pH | 9.5 | Strip |
| IADC Code | 1.1.7 |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number | 748179 |  |  | Circulate Sample |  |  | PV / YP | 17/23 | Cp/lb/100’ |
| Nozzles (32) | 3x12 |  |  | Casing |  |  | Gels | 3/9 | S/m |
| Depth in (m) | 1449 |  |  | Cementing |  |  | Sand | 0.5 | % Vol |
| Depth out (m) | 1775 |  |  | Wireline |  |  | Solids | 7.9 | % Vol |
| Total Metres | 326 |  |  | Circulate & Condition | 2.0 |  | Oil |  | % Vol |
| Hours | 48 |  |  | Rig Service/slip & cut |  |  | K+ | 22,967 | Mg/l |
| WOB (kg) | 12,000 |  |  | Test BOP's |  |  | Chlorides | 24,500 | Mg/l |
| RPM | 85 |  |  | Repairs |  |  | PHPA | 1.65 |  |
| Condition | 2-2-WT-A-E-1-NO-TD |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force | 7.39 |  |  | Wait On Cement |  |  | Daily Cost $ | 2,080 |
| Jet Velocity | 88.5 |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 81,133 |
| B.H.A.: | Bit, bit sub, 2x6-1/2” DC’s, stabilizer, XO, 16x6-1/2” DC’s, jars, 3x6-1/2” DC’s, 6x4-1/2” HWDP |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 2.5 | ° at | 1775 | m |  | Type | Amount |
| 0000 | 1400 | Drill 216mm hole from 1710m to 1775m |  |  | ° at |  | m |  | AMC PAC-R |  |
| 1400 | 1500 | Circulate hole clean. |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 1500 | 1730 | Wiper trip to 1531m. 20-30k overpull to 1600m. |  |  | ° at |  | m |  | Barite | 138 |
|  |  | RIH. Bridge at 1763m. Ream to 1775m |  |  | ° at |  | m |  | Drillzan | 1 |
| 1730 | 1830 | Circulate hole clean. |  |  | ° at |  | m |  | KCl Tech |  |
| 1830 | 1900 | Drop survey. Pump barite pill. |  |  | ° at |  | m |  | PHPA/Soda Ash | 3/4 |
| 1900 | 2400 | POH. Recover survey. |  |  | ° at |  | m |  | Caustic Soda | 2 |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure | 7600 | kPa |  | Pressure |  | kPa |
|  |  |  |  | A.V. DP | 43 | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC | 74 | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM | 54 |  | SPM |  |
|  |  |  |  | LPM | 1136 |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 800 |  | Size | 244 | mm |
|  |  |  |  | Class | A |  | Weight | 53.6 | kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 115 |  |
|  |  |  |  | % |  |  |  | Length | 1364 | m |
|  |  |  |  | Av. Wt | 15.6ppg |  | Shoe | 1366 | m |

,66