LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 23 | DFS: | 23 | DATE : | 27 Dec 2003 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1745m PBTD | LAST DEPTH : |  | 24 HR PROGRESS : | 0m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 57,109 | CUM. COST : $ | 1,375,798 |
| 0600 OPS : | Rig on Standby |
| Next 24 hr OPS: | Standby |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number |  |  |  | Drilling |  |  | Density | 1.22 | S.G. |
| Size (mm) |  |  |  | Tripping | 13.0 |  | Viscosity | 48 | Sec |
| Make |  |  |  | Surveys |  |  | Water Loss | 6.5 | Cc |
| Type |  |  |  | Reaming/work tight hole |  |  | pH | 9.0 | Strip |
| IADC Code |  |  |  | Testing/tools |  |  | Filter Cake | 1 | 32 nd |
| Serial Number |  |  |  | Circulate Sample |  |  | PV / YP | 18/26 | Cp/lb/100’ |
| Nozzles (32) |  |  |  | Casing | 1.0 |  | Gels | 3/10 | S/m |
| Depth in (m) |  |  |  | Cementing |  |  | Sand | 0.5 | % Vol |
| Depth out (m) |  |  |  | Wireline | 3.5 |  | Solids | 7.9 | % Vol |
| Total Metres |  |  |  | Circulate & Condition | 3.5 |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service/slip & cut | 1.0 |  | K+ | 22,967 | Mg/l |
| WOB (kg) |  |  |  | Test BOP's |  |  | Chlorides | 24,500 | Mg/l |
| RPM |  |  |  | Repairs |  |  | PHPA | 1.65 |  |
| Condition |  |  |  | Drill Out |  |  | ALC - 50 |  |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 4,505 |
| Jet Velocity |  |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 85,958 |
| B.H.A.: |  |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 2.5 | ° at | 1775 | m |  | Type | Amount |
| 0000 | 0030 | POH. |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0030 | 0130 | Lay down liner hanger running tool. |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 0130 | 0930 | Pick up 121mm DC’s and 89mm DP. RIH |  |  | ° at |  | m |  | Barite |  |
|  |  | Tag cement plug at 1742.9m |  |  | ° at |  | m |  | Drillzan |  |
| 0930 | 1300 | Clean out mud tanks. Mix 1.06 KCl brine. |  |  | ° at |  | m |  | KCl Tech |  |
| 1300 | 1700 | POH |  |  | ° at |  | m |  | PHPA/Soda Ash |  |
| 1700 | 2030 | Rig up Schlumberger. Run CBL. Rig down. |  |  | ° at |  | m |  | Caustic Soda |  |
| 2030 | 2130 | Slip and cut drilling line |  |  |  |  |
| 2130 |  | Rig on Standby |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure |  | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM |  |
|  |  |  |  | LPM |  |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 335 |  | Size | 178 | mm |
|  |  |  |  | Class | A |  | Weight | 38.7 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 48 |  |
|  |  |  |  | % |  |  |  | Length | 561 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1757 | m |

,66