LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 27 | DFS: | 27 | DATE : | 15 Jan 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1834.8m | LAST DEPTH : | 1832.4m | 24 HR PROGRESS : | 2.4m | PTD : | 1800m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 31,689 | CUM. COST : $ | 1,568,117 |
| 0600 OPS : | DST#2 |
| Next 24 hr OPS: | DST#2. POH. Reverse out recovery |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | CB-1 |  |  | Drilling |  |  | Density | 1.15 | S.G. |
| Size (mm) | 154 |  |  | Tripping | 10.0 |  | Viscosity | 34 | Sec |
| Make | Corpro |  |  | Surveys |  |  | Water Loss | 8.2 | Cc |
| Type | CP83 |  |  | Reaming/work tight hole |  |  | pH | 10.5 | Strip |
| IADC Code |  |  |  | Testing/tools | 7.0 |  | Filter Cake | 1 | 32 nd |
| Serial Number | 10052 |  |  | Circulate Sample |  |  | PV / YP | 6/8 | Cp/lb/100’ |
| Nozzles (32) |  |  |  | Casing |  |  | Gels | ‘1/2 | S/m |
| Depth in (m) | 1832.4 |  |  | Cementing |  |  | Sand | Tr | % Vol |
| Depth out (m) | 1834.8 |  |  | Wireline |  |  | Solids | 3.3 | % Vol |
| Total Metres | 2.4 |  |  | Circulate & Condition | 1.0 |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service/slip & cut |  |  | K+ | 59,444 | Mg/l |
| WOB (kg) |  |  |  | Test BOP's |  |  | Chlorides | 58,000 | Mg/l |
| RPM |  |  |  | Repairs | 1.5 |  | PHPA | 0.2 |  |
| Condition | 5% worn |  |  | Coring | 4.5 |  | ALC - 50 |  |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 117 |
| Jet Velocity |  |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 104,618 |
| B.H.A.: | Bit, boot basket, bit sub, 2 x 4-3/4” DC’s, stabilizer, 20 x 4-3/4” DC’s, drilling jars, 2 x 4-3/4” DC’s |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 0100 | RIH with core barrel. |  |  | ° at |  | m |  | AMC PAC-R |  |
| 0100 | 0200 | Circulate and drop diverting ball. |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 0200 | 0300 | Cut core #1 from 1832.4m to 1834.6m. |  |  | ° at |  | m |  | Barite |  |
| 0300 | 0430 | Rig repair. Investigate pump pressure loss. |  |  | ° at |  | m |  | Drillzan |  |
| 0430 | 0630 | Continue coring from 1834.6m to 1834.8m. (jammed) |  |  | ° at |  | m |  | KCl Tech |  |
| 0630 | 1100 | POH. |  |  | ° at |  | m |  | PHPA/Soda Ash | 1/0 |
| 1100 | 1230 | Recover 2.1m core (78%) |  |  | ° at |  | m |  | Caustic Soda |  |
| 1230 | 1730 | Replace packer rubbers. Make up DST tools. |  |  |  |  |
| 1730 | 2100 | RIH to 1250m. |  | PUMP 1 |  | PUMP 2 |
| 2100 | 2200 | Test set packer. Release packer. |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 2200 | 2300 | RIH. |  | Pressure |  | kPa |  | Pressure |  | KPa |
| 2300 | 2400 | Set packer at 1740m. Head up and test surface lines. |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM |  |
|  |  |  |  | LPM |  |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 335 |  | Size | 178 | mm |
|  |  |  |  | Class | A |  | Weight | 38.7 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 48 |  |
|  |  |  |  | % |  |  |  | Length | 561 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1757 | m |

,66