LAKES OIL Ltd

DAILY DRILLING REPORT

| WELL : | WOMBAT-1 | REPORT No. : | 42 | DFS: | 42 | DATE : | 30 Jan 2004 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1930mPBTD | LAST DEPTH : | 1930mpbtd | 24 HR PROGRESS : | 0m | PTD : | 2000m |
| TOTAL FUEL : |  | FUEL USAGE : |  | DAYCOST : $ | 34,438 | CUM. COST : $ | 2,375,212 |
| 0600 OPS : | Pick up DST tools for CHDST#4 |
| Next 24 hr OPS: | RIH. CHDST#4 |
| Site Personnel: | Peter Dwyer – Supervisor. |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number |  |  |  | Drilling |  |  | Density | 1.08 | S.G. |
| Size (mm) |  |  |  | Tripping |  |  | Viscosity |  | Sec |
| Make |  |  |  | Surveys |  |  | Water Loss |  | Cc |
| Type |  |  |  | Reaming/work tight hole |  |  | pH |  | Strip |
| IADC Code |  |  |  | Testing/tools | 24.0 |  | Filter Cake |  | 32 nd |
| Serial Number |  |  |  | Circulate Sample |  |  | PV / YP |  | Cp/lb/100’ |
| Nozzles (32) |  |  |  | Casing |  |  | Gels |  | S/m |
| Depth in (m) |  |  |  | Cementing |  |  | Sand |  | % Vol |
| Depth out (m) |  |  |  | Wireline |  |  | Solids |  | % Vol |
| Total Metres |  |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours |  |  |  | Rig Service/slip & cut |  |  | K+ |  | Mg/l |
| WOB (kg) |  |  |  | Test BOP's |  |  | Chlorides |  | Mg/l |
| RPM |  |  |  | Repairs |  |  | PHPA |  |  |
| Condition |  |  |  | Makeup brine |  |  | ALC - 50 |  |  |
| Impact Force |  |  |  | Wait On Cement |  |  | Daily Cost $ | 2,000 |
| Jet Velocity |  |  |  | Nipple Up BOPs |  |  | Cum Cost $ | 123,107 |
| B.H.A.: |  |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  |  | ° at |  | m |  | Type | Amount |
| 0000 | 1230 | Shut-In CHDST#3. Pull free at 1222hrs |  |  | ° at |  | m |  | AMC PAC-R |  |
| 1230 | 1430 | Reverse out 2bbl recovery. Increase wt to 1.08 SG. |  |  | ° at |  | m |  | Sodium Sulphite |  |
| 1430 | 1800 | POH |  |  | ° at |  | m |  | Wildcat 420 |  |
| 1800 | 2100 | Service and lay down DST tools |  |  | ° at |  | m |  | Drillzan |  |
| 2100 | 2200 | Wait on orders |  |  | ° at |  | m |  | KCl Tech | 160 |
| 2200 | 2400 | Rig up Reeves wireline. Run gauge ring to 1500m. |  |  | ° at |  | m |  | PHPA/Soda Ash |  |
|  |  |  |  |  | ° at |  | m |  | Caustic Soda |  |
|  |  |  |  | PUMP 1 |  | PUMP 2 |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure |  | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  |  |  | SPM |  |  | SPM |  |
|  |  |  |  | LPM |  |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks | 122 |  | Size | 114 | mm |
|  |  |  |  | Class | A |  | Weight | 17.3 | Kg/m |
|  |  |  |  | % |  |  |  | Grade | K55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 26 |  |
|  |  |  |  | % |  |  |  | Length | 327 | m |
|  |  |  |  | Av. Wt | 15.8ppg |  | Shoe | 1989 | m |

,66