## summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-11-28
PROGRAM
Customer |  | Beach Petroleum |  | Test Type |  | Formation Testing
Customer Representative |  | Phil |  | Test Operator |  | R. McQuatt
Well Name |  | Glenaire #1 |  | Assistant |  | S. Cox
Formation |  | Pretty Hill |  | Crew |  | Penola 1
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Separator |  | 76
F / SI .THP | n/a | n/a | Serial and Type |  | Test Tank |  | n/a
Pcsg | n/a | n/a | Gas Detector | Drageor | On-Site office |  | n/a
Icsg | n/a | n/a | Genset | n/a | Crane truck |  | 198
Scsg | n/a | n/a | Vehicle No. | 189 | Crane truck Kms. |  | 0
|  |  | Vehicle Km's | 70 | Accommodations |  | n/a
SEQUENCE OF EVENTS
24 Hr Summary : |  | 09:30 Depart Penola for location. 10:00 Arrive on location. Hold tool box talk and safety meeting. 10:05 Standby until further notice. 15:15 Released until morning. Depart location. 16:00 Generate Reports.
Forward Plan : |  | Begin Perforating operations.
Time | Description
09:30 | Depart Penola for location. | [6 empty] | 1
10:00 | Arrive on location. Hold tool box talk and safety meeting. | [6 empty] | 1
10:05 | Standby until further notice. | [6 empty] | 1
15:15 | Released until morning. Depart location. | [6 empty] | 1
16:00 | Generate Reports. | [6 empty] | 1
1
1
1
1
1
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
| PRISM control information | Rev 1.0
Date | 2007-11-28
Contractor | SGS Upstream
Rig/crew | Penola 1
Well | Glenaire #1
Type of operation | Formation Testing
24 Hour summary | 09:30 Depart Penola for location. 10:00 Arrive on location. Hold tool box talk and safety meeting. 10:05 Standby until further notice. 15:15 Released until morning. Depart location. 16:00 Generate Reports.
Forward plan | Begin Perforating operations.
Archive file name | glenaire_#1_2007-11-28_formation_testing_penola_1.xls