## summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-12-01
PROGRAM
Customer |  | Beach Petroleum |  | Test Type |  | Formation Testing
Customer Representative |  | Phil |  | Test Operator |  | R. McQuatt
Well Name |  | Glenaire #1 |  | Assistant |  | S. Cox
Formation |  | Pretty Hill |  | Crew |  | Penola 1
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Separator |  | 76
F / SI .THP | n/a | n/a | Serial and Type |  | Test Tank |  | n/a
Pcsg | n/a | n/a | Gas Detector | Drageor | On-Site office |  | n/a
Icsg | n/a | n/a | Genset | n/a | Crane truck |  | 198
Scsg | n/a | n/a | Vehicle No. | 189 | Crane truck Kms. |  | 0
|  |  | Vehicle Km's | 70 | Accommodations |  | n/a
SEQUENCE OF EVENTS
24 Hr Summary : |  | 0815 Depart Penola for location. 0845 Arrive on location. Hold tool box talk and safety meeting. 0905 Remove digital wellhead pressure recorder. 1000 Begin to RIH with perf. Guns. 1140 Perf. Guns fired (25psi on wellhead) 1220 Guns at surface. Shut in Master valve. 1335 Begin to RIH with perf. Guns. 1517 Shoot Perf. Guns. (27psi on wellhead) 1600 Guns at surface. Shut in Master valve. 1640 RIH with Guages. 1700 Replace digital wellhead pressure recorder. 1715 Guages on bottom. Secure wellhead. Clean up tools and depart location. 1830 Generate Reports.
Forward Plan : |  | Swab. Possible flow.
Time | Description
0815 | Depart Penola for location. | [6 empty] | 1
0845 | Arrive on location. Hold tool box talk and safety meeting. | [6 empty] | 1
0905 | Remove digital wellhead pressure recorder. | [6 empty] | 1
1000 | Begin to RIH with perf. Guns. | [6 empty] | 1
1140 | Perf. Guns fired (25psi on wellhead) | [6 empty] | 1
1220 | Guns at surface. Shut in Master valve. | [6 empty] | 1
1335 | Begin to RIH with perf. Guns. | [6 empty] | 1
1517 | Shoot Perf. Guns. (27psi on wellhead) | [6 empty] | 1
1600 | Guns at surface. Shut in Master valve. | [6 empty] | 1
1640 | RIH with Guages. | [6 empty] | 1
1700 | Replace digital wellhead pressure recorder. | [6 empty] | 1
1715 | Guages on bottom. Secure wellhead. Clean up tools and depart location. | [6 empty] | 1
1830 | Generate Reports. | [6 empty] | 1
1
1
1
1
1
1
1
1
1
1
1
1
CUSTOMER REPRESENTATIVE SIGNATURE

## Test Results
ty Hill |  |  | Customer: |  | Beach Petroleum |  | Well Name: |  | Glenaire 1 |  |  | Formation: |  | Pretty Hills
|  |  | Perforations: |  |  |  | Type Of Test: |  | Formation Testing |  |  | Operator: |  | R. McQuatt
|  |  | Date Of Test: |  | 2007-11-30 | [6 empty] | Control No.:
TIME |  |  | WELLHEAD DATA |  |  |  | SEPARATOR |  | FLOW RATES |  |  | CUMULATIVE PRODUCTION
Date | Time | Elapsed | Tubing | Annulus | Wellhead | Choke | Pressure | Temp | Gas | Oil | Water | Gas | Oil | Water | W.G.R. | O.G.R.
|  | Time | Pressure | Pressure | Temp | Size |  |  | Flow | Flow | Flow
[9 empty] | Rate | Rate | Rate |  |  |  | (BBLS/ | (BBLS/
|  | (Hours) | (PSI) | (PSI) | (ºC) | (64th) | (PSI) | (ºC) | (MMSCFD) | (BPD) | (BPD) | (MMSCF) | (BBLS) | (BBLS) | MMSCF) | MMSCF)
1/12/07 | 1140 | 44.8333 | 25 |  |  | 0
1/12/07 | 1145 | 44.9167 | 25 |  |  | 0
1/12/07 | 1200 | 45.1667 | 26 |  |  | 0
1/12/07 | 1215 | 45.4167 | 26 |  |  | 0
1/12/07 | 1517 | 48.45 | 26 |  |  | 0
1/12/07 | 1530 | 48.6667 | 25 |  |  | 0
1/12/07 | 1545 | 48.9167 | 25 |  |  | 0
1/12/07 | 1600 | 49.1667 | 25 |  |  | 0
Test Results

## PRISM
| PRISM control information | Rev 1.0
Date | 2007-12-01
Contractor | SGS Upstream
Rig/crew | Penola 1
Well | Glenaire #1
Type of operation | Formation Testing
24 Hour summary | 0815 Depart Penola for location. 0845 Arrive on location. Hold tool box talk and safety meeting. 0905 Remove digital wellhead pressure recorder. 1000 Begin to RIH with perf. Guns. 1140 Perf. Guns fired (25psi on wellhead) 1220 Guns at surface. Shut in Master valve. 1335 Begin to RIH with perf. Guns. 1517 Shoot Perf. Guns. (27psi on wellhead) 1600 Guns at surface. Shut in Master valve. 1640 RIH with Guages. 1700 Replace digital wellhead pressure recorder. 1715 Guages on bottom. Secure wellhead. Clean up tools and depart location. 1830 Generate Reports.
Forward plan | Swab. Possible flow.
Archive file name | glenaire_#1_2007-12-01_formation_testing_penola_1.xls