DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 24, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 237 | 363 |
| --- | --- | --- |
| CAMERON | 5492 | 5513 |
| HALLIBURTON | 3314 | 3313 |
| SCHLUMBERGER | 2094 | 2093 |
| ISDL | 237 | 647 |
| ISS | 29 | 2339 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: June 24, 2006

Supervisor:.	Bennett, James M.

Davis, Brian.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 3.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $208,647 |  |  |
| Total Cost: | $794,142 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 1960.00/1396.43 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Circ & repair #1 shaker motor, change shaker screens, Held pit drill, Drill 8½" hole from 1558m to 1760m. Circulate bottoms up. Drill 8½" hole from 1760m to 1903m. Change #2 shaker screens, Drill 8½" hole from 1903m to 1960m. |
| Current: | Drill 8½" hole @ 1960m. |
| Planned: | Drill & Survey 8½" Production Hole. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 25, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 238 | 363 |
| --- | --- | --- |
| CAMERON | 5493 | 5513 |
| HALLIBURTON | 3315 | 3314 |
| SCHLUMBERGER | 2095 | 2094 |
| ISDL | 238 | 647 |
| ISS | 30 | 2339 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: June 25, 2006

Supervisor:.	Bennett, James M.

Davis, Brian.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $221,754 |  |  |
| Total Cost: | $1,015,896 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2450.00/1717.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Drilled 8½" hole to 1989m. Changed shaker screens to 80 mesh. Held pit drills. Pumped Hi-Vis sweeps as required. Drilled 8½" hole to2450m. |
| Current: | Drill 8½" Production Hole @ 2450m. |
| Planned: | Drill 8½" Production Hole to ~2778m. POH to change Saver Sub for 5" DP. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 26, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 239 | 363 |
| --- | --- | --- |
| CAMERON | 5494 | 5513 |
| HALLIBURTON | 3316 | 3315 |
| SCHLUMBERGER | 2096 | 2095 |
| ISDL | 239 | 647 |
| ISS | 31 | 2339 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: June 26, 2006

Supervisor:.	Bennett, James M.

Davis, Brian.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 5.5 | AFE Cost/Days: | $4,208,000 |
| Daily Cost: | $219,676 |  |  |
| Total Cost: | $1,235,572 | Planned MD/TVD: | 3438.00/2363.00 |
| Casing Size: |  | Actual MD/TVD: | 2794.00/1942.36 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31A |
| --- | --- |
| Management Summary: | Drilled 8½" Hole to 2794m. Held Pit Drills. Serviced Work Boat. Pump sweep, Circulate hole clean. POH to 1270m, Pump sweep, Circulate hole clean. |
| Current: | Circulate hole clean. |
| Planned: | Change saver sub for 5" DP, RIH to bottom, Drill 8½" Hole to 3438m (TD) |