DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 22, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 235 | 363 |
| --- | --- | --- |
| CAMERON | 5490 | 5512 |
| HALLIBURTON | 3312 | 3311 |
| SCHLUMBERGER | 2092 | 2091 |
| ISDL | 235 | 647 |
| ISS | 27 | 2338 |

Well: WKF_W31A

Rig/Contractor: 	Rig 453	Report Date: June 22, 2006

Supervisor:.	Campbell, Glenn R.

Davis, Brian.

| AFE Number: | L0501G655 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: |  | AFE Cost/Days: | $6,500,000 |
| Daily Cost: | $226,157 |  |  |
| Total Cost: | $391,134 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31 |
| --- | --- |
| Management Summary: | M/up BHA & RIH to 497m. Power Choke Drill. RIH to 1243m. Displace to 9.0 ppg mud. Rig Service. Held trip drills. Drill cement to 1300m. Circ & condition mud. Spud Well, Time drill & kickoff cement plug. Pump sweep & Circulate. |
| Current: | Circulate Hole Clean & Condition Mud. |
| Planned: | Conduct PIT to 13 ppg. Drill & survey 8½" Production Hole. |