DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 17, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 230 | 363 |
| --- | --- | --- |
| CAMERON | 5485 | 5510 |
| HALLIBURTON | 3308 | 3307 |
| SCHLUMBERGER | 2087 | 2086 |
| ISDL | 230 | 647 |
| ISS | 22 | 2333 |

Well: WKF_W19A

Rig/Contractor: 	Rig 453	Report Date: June 17, 2006

Supervisor:.	Campbell, Glenn R.

Davis, Brian.

| AFE Number: | L0501G653 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 2.1 | AFE Cost/Days: | $5,200,000.00 |
| Daily Cost: | $31,859 |  |  |
| Total Cost: | $3,922,047 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2648.10 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W19A |
| --- | --- |
| Management Summary: | Pull BPV. Install pump-in flange for TCP gun detonation. Clear pipedeck & rig floor. P/u equipment after crane shutdown due to weather. Reinstate deluge & wellhead grating. Rig released to WKF W-31 P&A at 08:30 Hrs. |
| Current: | Rig released to WKF W-31 P&A at 08:30 Hrs. |
| Planned: | Rig released to WKF W-31 P&A at 08:30 Hrs. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 17, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 230 | 363 |
| --- | --- | --- |
| CAMERON | 5485 | 5510 |
| HALLIBURTON | 3308 | 3302 |
| SCHLUMBERGER | 2087 | 2086 |
| ISDL | 230 | 647 |
| ISS | 22 | 2336 |

Well: WKF_W31

Rig/Contractor: 	Rig 453	Report Date: June 17, 2006

Supervisor:.	Campbell, Glenn R.

Davis, Brian.

| AFE Number: | L0501G656 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | .9 | AFE Cost/Days: | $1,000,000 |
| Daily Cost: | $166,590 |  |  |
| Total Cost: | $1,000,000 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 3729.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31 Plug & Abandonment |
| --- | --- |
| Management Summary: | WOW. Stump test BOP. Skid rig over W-31 slot. Service work boat. Re-instate rig access & services. Dress HP riser. |
| Current: | Removing deck grating to nipple up BOP. |
| Planned: | N/U & Test BOP. Set abandonment cement plug 1425 to 1375m. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 18, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 231 | 363 |
| --- | --- | --- |
| CAMERON | 5486 | 5510 |
| HALLIBURTON | 3309 | 3302 |
| SCHLUMBERGER | 2088 | 2087 |
| ISDL | 231 | 647 |
| ISS | 23 | 2336 |

Well: WKF_W31

Rig/Contractor: 	Rig 453	Report Date: June 18, 2006

Supervisor:.	Campbell, Glenn R.

Davis, Brian.

| AFE Number: | L0501G656 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 1.9 | AFE Cost/Days: | $1,000,000 |
| Daily Cost: | $166,590 |  |  |
| Total Cost: | $1,000,000 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 3729.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31 Plug & Abandonment |
| --- | --- |
| Management Summary: | WOW. Stump test BOP. Skid rig over W-31 slot. Service work boat. Re-instate rig access & services. Dress HP riser. |
| Current: | Removing deck grating to nipple up BOP. |
| Planned: | N/U & Test BOP. Set abandonment cement plug 1425 to 1375m. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS June 19, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 232 | 363 |
| --- | --- | --- |
| CAMERON | 5487 | 5510 |
| HALLIBURTON | 3310 | 3302 |
| SCHLUMBERGER | 2089 | 2088 |
| ISDL | 232 | 647 |
| ISS | 24 | 2336 |

Well: WKF_W31

Rig/Contractor: 	Rig 453	Report Date: June 19, 2006

Supervisor:.	Campbell, Glenn R.

Davis, Brian.

| AFE Number: | L0501G656 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 2.9 | AFE Cost/Days: | $1,000,000 |
| Daily Cost: | $165,581 |  |  |
| Total Cost: | $514,491 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 3729.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W31 |
| --- | --- |
| Management Summary: | Circ hole clean. POH. Service Rig. Held trip drills. M/up csg cutter & RIH. Tag cmt @ 1375m. Cut csg @ 1372m. Circ hole clean. POH & L/dn cutter. M/up & engage csg spear. Free csg w/ 320k. P/up 3m & circ BU. R/up WFD. L/out casing. |
| Current: | Laying out 9-5/8" Casing from 1372m. |
| Planned: | L/out 9-5/8" Casing. Set kickoff cement plug. |