DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 23, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 280 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 202 | 202 |
| CAMERON | 1755 | 1755 |
| HALLIBURTON | 3559 | 3559 |
| SCHLUMBERGER | 2464 | 2464 |
| ISS | 272 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 23, 2007

Supervisor:	Davis, Brian

Spence, Robert

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 42.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $7,291,779 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | AWU crew members departed platform on 10:00 hr flight to onshore for Com's/EB meeting, back on 15:00 hr flight. Completed Isstallation of v-door rollar in mast, clear rig floor of excess equip., Install active and suction pits 600V switch boards, test run agitators and trip tank motors, hook up 2 rig air compressors and test run same, Prepare for DNV inspection. Rig up 80% complete |
| Current: | General rig up operation |
| Planned: | Continue rig up |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 23, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 280 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 202 | 202 |
| CAMERON | 1755 | 1755 |
| HALLIBURTON | 3559 | 3559 |
| SCHLUMBERGER | 2464 | 2464 |
| ISS | 272 | 2357 |

Well: HLA_A24

Rig/Contractor: 	Rig 453	Report Date: February 23, 2007

Supervisor:	Bareswill, J R (Dicky)

Smith, Gary G

| AFE Number: AFE Number: | L0501G208 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 29.85 | AFE Cost/Days: | $7,818,363 |
| Daily Cost: | $147,369 |  |  |
| Total Cost: | $8,017,687 | Planned MD/TVD: | 2,991.00/2,621.29 |
| Casing Size: |  | Actual MD/TVD: | 2,991.01/2,452.98 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A24 |
| --- | --- |
| Management Summary: | R/D Slickline unit, L/d landing jts and running tool. Install Cameron BPV. N/D Bops, N/U Cameron Tree, test tree and void area to 5000 psi-good test. Removed BPV, Replaced Deck Grating. Handed Well HLA 24 over to Production at 1330 hrs, 22 Feb. 2007. FRR at 1330 hrs 22 Feb 2007. Prepare rig for skid from HLA 24 to HLA 16 (8.5m to West). |
| Current: | Prepare to Skid to HLA 16 |
| Planned: | R/u on HLA 16 |