DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 9, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 294 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 216 | 216 |
| CAMERON | 1769 | 1769 |
| HALLIBURTON | 13 | 3570 |
| SCHLUMBERGER | 2478 | 2478 |
| ISS | 286 | 2357 |

Well: FTA_A12A

Rig/Contractor: 	Rig 175	Report Date: March 9, 2007

Supervisor:	Stead, Cory

Davis, Brian

| AFE Number: AFE Number: | L0501H001 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 1.21 | AFE Cost/Days: | $8,850,710 |
| Daily Cost: | $237,027 |  |  |
| Total Cost: | $274,486 | Planned MD/TVD: | 4,033.00 / 3,342.35 |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | L/out 4" test assembly. Continue general rig up operations. Secure deck grating. Install eyewash stations & safety showers. Continue testing SBM transfer lines for leaks in preparation for offloading SBM. Identify & lock/label SBM & dump valves. Rig commissioning ongoing. |
| Current: | General rig up operations. |
| Planned: | Cont. R/U. N/U stack & riser. Shell test. M/U cleanout BHA & RIH. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS MARCH 9, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 294 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 216 | 216 |
| CAMERON | 1769 | 1769 |
| HALLIBURTON | 13 | 3570 |
| SCHLUMBERGER | 2478 | 2478 |
| ISS | 286 | 2357 |

Well: HLA_A16A

Rig/Contractor: 	Rig 453	Report Date: March 9, 2007

Supervisor:	Bigby, Brigham

Campbell, Glenn R

| AFE Number: AFE Number: | L0501H210 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 9.13 | AFE Cost/Days: | $6,614,569 |
| Daily Cost: | $241,478 |  |  |
| Total Cost: | $2,951,133 | Planned MD/TVD: | 2,535.30 / 3,012.05 |
| Casing Size: |  | Actual MD/TVD: | 1,550.00 / |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16A |
| --- | --- |
| Management Summary: | PTSM's. Held pit drills. Drill, steer & survey 8-1/2" production hole from 1163m to 1550m. Rig service. |
| Current: | Rig Service. |
| Planned: | Continue to drill, steer & survey 8-1/2" production hole. |