## Report
| DAILY DRILLING REPORT | [12 empty] | 2006-10-26
49
WELL | Glenaire 01 ST1 |  |  |  | 24:00 DEPTH | 3700 |  |  | 24 HR PROG | 0 |  |  | CUM. COSTS | 168362.85
RIG | Ensign # 32 |  |  |  | FORMATION | Pretty Hill |  |  | PTD | 3945 |  |  | DAILY COSTS | 0
OP's TO 06:00 |  | Log #1 = FMS-GR, Log #2 = BHC-PEX-GR, rig down, pressure test BOP, RIH to shoe, Repairs, fault find wireing for "extend" operation on Top Drive.
REMARKS / FORWARD PLAN: |  | Pressure test rig floor surface equip., circ., RIH to bottom, Drill 1m of hole to evaluate torque / ROP w/ no mud motor, Circ. bottoms up, POOH to complete logs | [10 empty] | PERSONNEL ON SITE: |  | 38
LAST CASING |  | 7 | SET AT | 2998 | LOT | 13.8014 | MAASP |  | 1356.0851 |  | BOP TEST | 2006-10-26 |  | TEST DUE | 2006-11-09
87 |  | SAFETY | 1. Safety meeting | [9 empty] | WEATHER AM | Fine
|  |  | 2. Toolbox meeting | [9 empty] | PM | Fine
BIT INFORMATION |  |  |  | 13 |  |  |  |  | MUD PROPERTIES |  |  | OPERATION |  | HRS | CUM
WOB(kLb) | 0 | JET V(fps) |  | TOOL |  |  | LENGTH |  | Time | 2130 |  | BOP's / Wellhead |  |  | 36
RPM | 0 | H S I |  | DSX111GJW |  |  | 0.2 |  | Depth (m) | 3700 |  | Cementing |  |  | 8.5
BIT NUMBER |  | RR11 | 0 | Float sub |  |  | 0.91 |  | Temp (° C) | No Circ |  | Circ & Condition |  | 0.5 | 45
Size (in) |  | 6 |  | 14 x 4-3/4" dc's |  |  | 132.38 |  | Mud Type | KCL/PHPA/POL |  | Coring |  |  | 0
Make |  | Hyc |  | Dailey Drlg. Jars |  |  | 8.96 |  | Density (ppg) | 11.15 |  | D/O Cement |  |  | 12.5
Type |  | DSX111 |  | 3 x 4-3/4" dc's |  |  | 28.3 |  | ECD (ppg) |  |  | Drilling |  |  | 461
IADC Code |  |  |  | 9 x HWDP |  |  | 85.5 |  | Viscosity (sec) | 41 |  | FIT / LOT |  |  | 4
Serial Number |  | 112300 | [6 empty] | PV / YP (cp/lb) | 13 / 14 |  | Handle BHA |  | 0.5 | 14.5
T.F.A.( ") | [8 empty] | Gells (s/m) | 2 / 6 |  | Repairs |  |  | 73
Depth In (m) |  | 3700 | [6 empty] | API Filt. (cc) | 6.2 |  | Rig Service |  |  | 8
Depth Out (m) | [8 empty] | Cake (/32") | 1 |  | Rig up Csg./ Cmt. |  |  | 11
Total Meters | [8 empty] | Solids (% Vol) | 8.8 |  | Run Casing |  |  | 32.5
Hours | [8 empty] | Sand (% Vol) | Tr |  | Safety |  |  | 2
ROP | [8 empty] | MBT | 6.5 |  | Slip/Cut Drill Line |  |  | 8
Condition Out |  |  |  | BHA LENGTH (m) |  |  | 256.25 |  | pH (strip) | 9.5 |  | Survey |  |  | 36.5
FLOW DATA |  |  |  | BHA WEIGHT(kLb) |  |  | 32.6226 |  | Chlorides (mg/l) | 158000 |  | Test BOP |  | 4 | 28
CIRC. RATE (gpm) |  | 0 |  | STRING WT (kLb) |  |  | 190.8093 |  | KCL (% ) | 8 |  | Tight hole / Fishing |  |  | 0.5
AV - DP (fpm) |  | 0 |  | HOOK LOAD (kLb) |  |  |  |  | PHPA (ppb) | 0.79 |  | Tripping |  | 3 | 223.5
AV - DC (fpm) |  | 0 |  | WT BELOW JARS (kLb) |  |  | 0 |  | ALC - 50 (K) |  |  | Wait on Cement |  |  | 24.5
SPP (psi) |  |  |  | DRAG UP (kLb) |  |  |  |  | Circ. Vol. (Bbl) | 855 |  | Wash / Ream |  |  | 9.5
SPP (calculated) |  |  |  | DRAG DOWN (kLb) |  |  |  |  | CHEMICAL USAGE |  |  | Well Control |  |  | 3.5
PUMP #1 |  | PUMP #2 |  | TORQUE ON (Amps/Rel.) | [7 empty] | Well Test |  |  | 0
8-P-80 |  | 8-P-80 |  | TORQUE OFF (Amps/Rel.) | [7 empty] | Wiper Trip |  | 1 | 19.5
RATE | 0 | RATE | 0 | BULK PRODUCTS | [7 empty] | Wireline |  | 15 | 23.5
LINER | 5 | LINER | 5 | FUEL ON SITE |  | 33900 | [5 empty] | Other |  |  | 84
STROKE | 8.5 | STROKE | 8.5 | DAILY USAGE |  | 3350 | [5 empty] | TOTALS |  | 24 | 1169
|  |  |  | CUM. FUEL USED |  | 176988 | [5 empty] | DAILY MUD COSTS
SURVEYS |  |  |  | BARITES ON SITE |  | 50 | [5 empty] | CUM. MUD COSTS |  | 168362.85
|  |  |  | BARITES USED |  | 250 | [5 empty] | AFE COST - C&S
|  |  |  | MUD MIXED |  | 5302 | [5 empty] | AFE COST - P&A
|  |  |  | MUD LOSSES |  | 4405 | [5 empty] | AFE COST - C&C
HOURLY OPERATIONS SUMMARY 0000 to 2400
From | To | Description
0:00 | 1:00 | POOH to 1000m
1:00 | 1:30 | Present mud wt. = 11.1ppg, spot 60bbls weighted 14.5ppg mud (490m) equiv. mud wt. = 11.6ppg for hydrostatic @ 3192m
1:30 | 3:30 | Cont. POOH
3:30 | 4:00 | Flush out Mud motor with water, oil, break off bit, clear rig floor
4:00 | 12:30 | Rig up to log, Safety Meeting, run #1 = FMS - GR, run @ 04:50hrs, out @ 12:20hrs ( hole in good condition, run to bottom, no fill )
12:30 | 19:00 | Make up tools, Logging, run #2 = BHC-PEX-GR, run @ 12:50hrs, out @ 18:10hrs (loosing 1/2 bbl/ hr of mud to annulus) Rig Down
19:00 | 23:00 | Pull W.B., make up comb. test plug, RIH & set same, press. test BOP, 200psi low & 3500psi high, Conduct Accumulator Test, set W.B.
23:00 | 24:00 | Make up RR, DSX111, PDC, RIH to 256m
MAXIMUM GAS: |  | % @ m |  |  |  | BACKGROUND GAS: | % |  |  |  | CONNECTION GAS: | % |  | TRIP GAS: | %
| SUPERVISOR: | Brian Marriott |  |  |  |  | GEOLOGIST: | Dave Horner |  |  |  | MUD CO: | RMN Drilling Fluids