DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 07, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 279 | 363 |
| --- | --- | --- |
| CAMERON | 5532 | 5536 |
| HALLIBURTON | 3354 | 3353 |
| SCHLUMBERGER | 2134 | 2133 |
| ISDL | 279 | 647 |
| ISS | 67 | 2361 |

Well: WKF_W8

Rig/Contractor: 	Rig 453	Report Date: August 05, 2006

Supervisor:	Campbell, Glen R

Steel, George A

| AFE Number: | 40000455 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.3 | AFE Cost/Days: | $1,589,300 |
| Daily Cost: | $182,600 |  |  |
| Total Cost: | $762,705 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W8 |
| --- | --- |
| Management Summary: | Tag packer @ 2400m. Set P&A Plug #1. POH to 2311m & reverse clean. POH & l/out 2-7/8" tbg. Shell test BOP. RIH w/ 4" d/pipe. Slip & cut. RIH & tag TOC @ 2348.5m. P/test csg to 500psi. Circ to ISW. Held trip drills. |
| Current: | Circulating inhibited seawater. |
| Planned: | Lay cmt plug #2 at 945m-895m. POH. N/d BOP/riser & tbg spool. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 06, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 280 | 363 |
| --- | --- | --- |
| CAMERON | 5533 | 5536 |
| HALLIBURTON | 3355 | 3354 |
| SCHLUMBERGER | 2135 | 2134 |
| ISDL | 280 | 647 |
| ISS | 68 | 2361 |

Well: WKF_W8

Rig/Contractor: 	Rig 453	Report Date: August 06, 2006

Supervisor:	Campbell, Glen R

Steel, George A

| AFE Number: | 40000455 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 5.3 | AFE Cost/Days: | $1,589,300 |
| Daily Cost: | $177,111 |  |  |
| Total Cost: | $939,816 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 894.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W8 |
| --- | --- |
| Management Summary: | Spot ISW from 2348.5m to 800m. POH to 945m. Deploy CST. Set P&A plug #2 945m-895m. Circ clean & POH. N/d BOP/riser. N/d tubing spool. M/u fastlok riser & BOP. Dynamic shell test to 500psi. RIH w/ casing cutter to 891.5m. Held trip |
| Current: | Cutting 7-5/8" casing @ 891.5m. |
| Planned: | POH w/ casing cutter. RIH w/ casing spear. Fish & pull 7-5/8" casing. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 07, 2006

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 281 | 363 |
| --- | --- | --- |
| CAMERON | 5534 | 5536 |
| HALLIBURTON | 3356 | 3355 |
| SCHLUMBERGER | 2136 | 2135 |
| ISDL | 281 | 647 |
| ISS | 69 | 2361 |

Well: WKF_W8

Rig/Contractor: 	Rig 453	Report Date: August 07, 2006

Supervisor:	Campbell, Glen R

Steel, George A

| AFE Number: | 40000455 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 6.3 | AFE Cost/Days: | $1,589,300 |
| Daily Cost: | $191,693 |  |  |
| Total Cost: | $1,121,509 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 894.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W8 |
| --- | --- |
| Management Summary: | Cut 7-5/8" csg @ 891.5m. Circ clean. POH w/ cutter. P/u csg spear. Latch csg & POH. L/out cutter & csg spear. Shell test BOP, 3000/300psi. RIH w/ 4" DP. Lay plug #3. POH to 700m, reverse clean. . WOC. Held trip drills. |
| Current: | WOC. |
| Planned: | Tag cement. POH. N/down riser/BOP. Install abandonment flange. |