DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 22, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 296 | 363 |
| --- | --- | --- |
| CAMERON | 5549 | 5587 |
| HALLIBURTON | 3371 | 3370 |
| SCHLUMBERGER | 2151 | 24 |
| ISDL | 296 | 647 |
| ISS | 84 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 22, 2006

Supervisor:	Basset, Anthony A

Davis, Brian

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 7.0 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $190,733 |  |  |
| Total Cost: | $1,580,633 | Planned MD/TVD: | 2564.00/2403.00 |
| Casing Size: |  | Actual MD/TVD: | 2275.00/2412.60 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | POH t/ 1015m. Circ hole clean. POH to shoe. Circ hole clean. Slip & Cut. Rig Service. POH to surface. Rack back BHA. BCFT. M/up Precision Logging Tools. RIH, space out & deploy tools. |
| Current: | Commence logging operations. |
| Planned: | Log 8½" Production Hole. |