DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS August 30, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 104 | 363 |
| --- | --- | --- |
| CAMERON | 5556 | 5587 |
| HALLIBURTON | 3378 | 3377 |
| SCHLUMBERGER | 2158 | 24 |
| ISDL | 104 | 647 |
| ISS | 91 | 2367 |

Well: WKF_W21A

Rig/Contractor: 	Rig 453	Report Date: August 30, 2006

Supervisor:	Basset, Anthony A

Steel, George A

| AFE Number: | L0501G658 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 3.9 | AFE Cost/Days: | $5,120,000 |
| Daily Cost: | $115,696 |  |  |
| Total Cost: | $3,895,671 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2544.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W21A |
| --- | --- |
| Management Summary: | Cameron install tree & p/test same, OK. Cameron r/up lubricator & pull BPV. N/down lub & n/up w/line BOP, riser, & lubricator. RIH & open SSD, RIH & set sand separation tool. R/D w/line, reinstate grating. Release rig. |
| Current: | See WKF W-6A P&A report. |
| Planned: | See WKF W-6A P&A report. |