DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 24, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 281 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 203 | 203 |
| CAMERON | 1756 | 1756 |
| HALLIBURTON | 3560 | 3560 |
| SCHLUMBERGER | 2465 | 2465 |
| ISS | 273 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 24, 2007

Supervisor:	Davis, Brian

Spence, Robert

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 43.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $7,473,762 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Flights Cancelled due to fog, unable to get additional 3rd party personnel onboard to assist with rig up. ISDL night shift short changed, day shift crew change (4 men short on Night shift due to unavailability of helicopter seating). Complete fitting of lagging to generator exhaust, install 90* elbows for koomey lines to rig floor, test run shale shakers, test run degasser, run swaco stroke counters and organized wires. Installing lifts for haliburton cementing. Cont. working on Cat engine shutdown for DNV. Rig up 82% complete |
| Current: | General rig up operation |
| Planned: | Continue rig up |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 24, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 281 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 203 | 203 |
| CAMERON | 1756 | 1756 |
| HALLIBURTON | 3560 | 3560 |
| SCHLUMBERGER | 2465 | 2465 |
| ISS | 273 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: February 24, 2007

Supervisor:	Bareswill, J R (Dicky)

Smith, Gary G

| AFE Number: AFE Number: | 40000448 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 1.65 | AFE Cost/Days: | $2,177,350 |
| Daily Cost: | $207,821 |  |  |
| Total Cost: | $341,340 | Planned MD/TVD: | 2,581.00 / |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | R/u Access stairways/steps. Check well pressures-O, Install Cameron BPV in tbg hgr, Remove Deck Grating, Remove Tree, Install spacer spools, Bops. Construction installed cable to riser to prevent lateral movement. Install casing rams in top pipe ram, perform Bop function test and accumulator inspection. |
| Current: | M/u 5 1/2" tbg/landing jts. |
| Planned: | Shell test bops, Pull WR-SSSV |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 25, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 282 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 204 | 204 |
| CAMERON | 1757 | 1757 |
| HALLIBURTON | 3561 | 3561 |
| SCHLUMBERGER | 2466 | 2466 |
| ISS | 274 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 25, 2007

Supervisor:	Davis, Brian

Stead, Cory

Spence, Robert

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 44.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $7,655,745 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Cont. installing 3" cmt line in derrick mast, construct bleed off manifold on mud pumps, install choke/kill lines, install south end stairway from rig floor to pipe deck, install lift rams on bops and safety slings, performing shut downs for DNV inspections.service M/V Far Scandia, clear of pipe deck and prepare deck for cargo. Rig up 84% complete |
| Current: | General rig up operations |
| Planned: | Continue rig up |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 25, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 282 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 204 | 204 |
| CAMERON | 1757 | 1757 |
| HALLIBURTON | 3561 | 3561 |
| SCHLUMBERGER | 2466 | 2466 |
| ISS | 274 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: February 25, 2007

Supervisor:	Bareswill, J R (Dicky)

Smith, Gary G

| AFE Number: AFE Number: | 40000448 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 2.65 | AFE Cost/Days: | $2,177,350 |
| Daily Cost: | $207,821 |  |  |
| Total Cost: | $549,161 | Planned MD/TVD: | 2,581.00 / |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | Opened SSSV, no pressure on tbg or PA. Pulled SSSV with Halliburton, Backed out tbg hanger locking screws on tbg head, Ran Schl GR to 760m, Safety Mtg/JSA on handling/running Chemical Cutter, Ran Chemical cutter, correlated, Had misfire on Chem Cutter, Pooh to inspect tool, replace injector/adaptor, RBIH and cut tbg at 674m, no pressure noted on tbg and PA, R/d Schlumberger. Removed control line from tbg. spool, Displacing ISW from 674m with 9.5 ppg mud. |
| Current: | Circulating 9.5 ppg mud after cutting 5 1/2" tbg |
| Planned: | Pull 5 1/2" Tbg |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 26, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 283 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 205 | 205 |
| CAMERON | 1758 | 1758 |
| HALLIBURTON | 3562 | 3562 |
| SCHLUMBERGER | 2467 | 2467 |
| ISS | 275 | 2357 |

Well: FTA _A12a

Rig/Contractor: 	Rig 175	Report Date: February 26, 2007

Supervisor:	Davis, Brian

Stead, Cory

Spence, Robert

| AFE Number: AFE Number: | L0501H000 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 45.71 | AFE Cost/Days: | $10,210,000 |
| Daily Cost: | $181,983 |  |  |
| Total Cost: | $7,837,728 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | FTA_A12a |
| --- | --- |
| Management Summary: | Install safety slings on BOPs, continue to hook up mud pump pop off manifold, install choke line to BOPs, hook up oil base mud hose for boat take on, Can-Rig service hand conduct test on Top drive system, prepare pipe deck for bringing on equip., prepare rig package to be skidded over well bay, and continue with DNV rig inspection. |
| Current: | General rig up operations |
| Planned: | Continue rig up |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS FEBRUARY 26, 2007

SAFETY:

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| ISDL RIG 453 | 283 | 363 |
| --- | --- | --- |
| ISDL RIG 175 | 205 | 205 |
| CAMERON | 1758 | 1758 |
| HALLIBURTON | 3562 | 3562 |
| SCHLUMBERGER | 2467 | 2467 |
| ISS | 275 | 2357 |

Well: HLA_A16

Rig/Contractor: 	Rig 453	Report Date: February 26, 2007

Supervisor:	Bareswill, J R (Dicky)

Smith, Gary G

| AFE Number: AFE Number: | 40000448 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days on AFE | 3.65 | AFE Cost/Days: | $2,177,350 |
| Daily Cost: | $239,372 |  |  |
| Total Cost: | $788,533 | Planned MD/TVD: | 2,581.00 / |
| Casing Size: |  | Actual MD/TVD: |  |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | HLA_A16 |
| --- | --- |
| Management Summary: | L/d 5 1/2" tubing cut from 674m, R/U Schl-ran GR-JB, recovered 3 control line protectors with JB, Scraped area 622-632m 6 times, set 7 5/8" EZSV at 629mELM, Pooh with W/L, tested 7 5/8" x EZSV to 1000 psi for 5 min., good test. R/d Schl. N/D Bops, Removed Shaffer tbg head, Prepared 7 5/8" casing slips for removal, install DSA on Riser spool, N/U DSA-Riser Spool to A section. |
| Current: | N/u Bops |
| Planned: | Cut 7 5/8" casing |