DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 04, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 107 | 363 |
| --- | --- | --- |
| CAMERON | 1582 | 1582 |
| HALLIBURTON | 3370 | 3370 |
| SCHLUMBERGER | 2320 | 2320 |
| ISDL | 107 | 647 |
| ISS | 96 | 2328 |

Well: WKF_W6

Rig/Contractor: 	Rig 453	Report Date: September 02, 2006

Supervisor:	Campbell, Glenn R

Steel, George A

| AFE Number: | 40000459 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 3.3 | AFE Cost/Days: | $1,576,600 |
| Daily Cost: | $210,520 |  |  |
| Total Cost: | $662,305 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 2785.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6, P&A |
| --- | --- |
| Management Summary: | Displace to ISW. POOH 3½" EUE tbg to SSSV. RIH 3½" on 4" d/pipe, tag packer 2887m. Spot 15.1 bbls cmt plug on bottom & POOH. L/out 3½ EUE tbg to 1399m. RIH on 4", tag cmt @ 2785m. P/test to 500psi. Circ ISW. Trip drills. |
| Current: | Circulating well to ISW. |
| Planned: | POOH to 820m. Pump cmt plug#2. POOH. Remove B-section, n/up BOP. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 04, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 108 | 363 |
| --- | --- | --- |
| CAMERON | 1583 | 1583 |
| HALLIBURTON | 3371 | 3371 |
| SCHLUMBERGER | 2321 | 2321 |
| ISDL | 108 | 647 |
| ISS | 97 | 2328 |

Well: WKF_W6

Rig/Contractor: 	Rig 453	Report Date: September 03, 2006

Supervisor:	Campbell, Glenn R

Steel, George A

| AFE Number: | 40000459 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 4.3 | AFE Cost/Days: | $1,576,600 |
| Daily Cost: | $192,111 |  |  |
| Total Cost: | $854,416 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 770.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6, P&A |
| --- | --- |
| Management Summary: | Displace well to ISW. POOH with 4"DP to 1399m. POOH with 3½" tbg to 696m. RIH on 4"DP to 820m & drop CST. Pump 7.7bbl cmt slurry. POOH to 770m & reverse clean. POOH 3½" tbg, N/down BOP & B-section. Trip drills. |
| Current: | Removing seized bolts from A-section flange. |
| Planned: | N/up BOP & p/test. RIH csg cutter & cut csg +/-768m. POOH. Pull csg. |

DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 04, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 109 | 363 |
| --- | --- | --- |
| CAMERON | 1584 | 1584 |
| HALLIBURTON | 3372 | 3372 |
| SCHLUMBERGER | 2322 | 2322 |
| ISDL | 109 | 647 |
| ISS | 98 | 2328 |

Well: WKF_W6

Rig/Contractor: 	Rig 453	Report Date: September 04, 2006

Supervisor:	Campbell, Glenn R

Steel, George A

| AFE Number: | 40000459 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 5.3 | AFE Cost/Days: | $1,576,600 |
| Daily Cost: | $174,979 |  |  |
| Total Cost: | $1,029,395 | Planned MD/TVD: |  |
| Casing Size: |  | Actual MD/TVD: | 776.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6, P&A |
| --- | --- |
| Management Summary: | N/up riser/BOP. Dynamic p/test to 1000psi. M/up cutter, RIH, tag cmt @ 776m. Cut csg @ 773.5m. Circ well clean. POH, l/out cutter. P/up csg spear, latch & pull csg free. Circ clean & POH w/ csg. WOW. Trip drills. |
| Current: | Circulate bottoms up. |
| Planned: | Complete POH w/ casing. Pressure test BOP. RIH & set cement plug#3. WOC |