DRILLING / WELLWORK REPORT 24HRS TO 0500 HRS September 22, 2006

SAFETY

DAYS SINCE LAST TRI:	PREVIOUS BEST TRI PERIOD

| RIG 453 | 127 | 363 |
| --- | --- | --- |
| CAMERON | 1602 | 1602 |
| HALLIBURTON | 3390 | 3390 |
| SCHLUMBERGER | 2331 | 2331 |
| ISDL | 127 | 647 |
| ISS | 116 | 2331 |

Well: WKF_W6A

Rig/Contractor: 	Rig 453	Report Date: September 22, 2006

Supervisor:	Basset, Anthony A.

Bennett, James M.

| AFE Number: | L0501G659 | Ave Angle: |  |
| --- | --- | --- | --- |
| Days to Complete: | 15.7 | AFE Cost/Days: | $6,291,200 |
| Daily Cost: | $ 180,527 |  |  |
| Total Cost: | $ 3,304,808 | Planned MD/TVD: | 3477.00/2368.00 |
| Casing Size: |  | Actual MD/TVD: | 3477.00/2371.00 |
| Mud Weight: |  | Tubing Size: |  |

| Objective: | WKF_W6A |
| --- | --- |
| Management Summary: | Pump sweep, circulate hole clean. POOH from 1397m to 680m. Conduct rig service. Pump sweep, circulate hole clean. Operations suspended due to platform fire pumps shut down. Reduce manning on WKF. Relocate 3rd Party Contractors to KFB. Monitor well whilst conduct maintenance on equipment. Circulate and condition mud every 6 hours. |
| Current: | Wait on platform fire pump engine changeout |
| Planned: | Wait on fire pump maintenance. Wiper trip. Run 7: casing. |