WEEKLY REPORT

Week Ending		20 September 2009

_______________________________________________________________________________

Well			GV Leishman 2

Location		As drilled

753312 m E	5873009 m N	Zone 54	(GDA 94)

Drilling Contractor 	Titeline Pty Ltd, Ballarat (Rig No.13)

Well Depth		317.8 metres		Target depth

Well Details		0 – 4.0 m		Open Hole 	170mm

4.0 – 85.3 m		PQ Core

85.3 – 130.2 m	Open Hole	PCD

130.2 – 135.1 m	HQ Core	no core recovered

135.1 – 147.0 m	Open hole	PCD

147.0 – 317.8 m	HQ Core

Casing			0 – 4.0 m 	PVC	150mm

0 – 179.0 m	HW

0 – 317.8 m	Poly casing	63mm

Other	Rig move delayed. See below.

________________________________________________________________________________

Safety	Manual handling incident. (18 September 2009).Drill offsider hurt back when lifting “Offsider Platform”. Medical treatment. Incident reported to Worksafe. Following an assessment of the incident by Titeline Safety to Geogen and Worksafe, the rig commenced moving to GV Pastoria 1, 19 September 2009. Further medical assessment of the injury will be made on 21 September 2009. The incident will be classified following the assessment.

Environment	The site refurbishment of GV Cameron 1/2 was delayed due to poor weather conditions. The site and approaches to the site were too wet and boggy. The site and the approaches will be allowed to dry out before another attempt will be made to complete refurbishment of the site.

Landholder Issues

No issues to report

Other		GV Leishman 2 commenced drilling on 9 September 2009

GV Leishman 2 completed drilling on 17 September 2009

Following completion of GV Leishman 2 the remainder of the drilling program is planned to be conducted on a single shift basis.

GV Pastoria 1 is expected to commence drilling 21 September 2009. The expected order of drilling is GV Pastoria 1, GV Baynton 1 and GV Marong 1.

Kate Parnell will take over day to day responsibilities for the remainder of the drilling program as of 22 September 2009, following completion of the double shift program. Rob Murphy is being transferred.

Rob Murphy

Geogen Victoria

Ballarat Operations