| Date: | 19 Oct 2009 | Report Number: | 3 |
| --- | --- | --- | --- |
| Report Period: | 0000-2400 Hours | Last Casing Shoe: | 569.44 mMDRT |
| Depth @ 2400hrs: | 572.5 mMDRT | Last Casing Size: | 762 (30”) |
| Previous 2400hr depth: | 0 mMDRT | Current Bit Size: | 660/914 mm (26”/36”) |
| Progress: | 48 m | FIT: | N/A |
| Lag Depth: | Returns to seafloor | Mud Weight: | 1.04 sg |
| Water Depth: | 503.0 m LAT | ECD: | N/A |
| RT: | 21.5 m | Mud Type: | Hi-Vis PHG/Guar Gum |
| Last Survey Depth: | N/A | Mud Chlorides: | N/A |
| Deviation: | N/A | Est. Pore Press: | 1.03 sg EMW |

## OPERATIONS SUMMARY

| 24 HOUR SUMMARY TO MIDNIGHT: | Made up 914 mm (36”) spud BHA. Connected TGB to bit. Ran TGB to sea bed on BHA. Spudded Somerset-1 well at 11:30 hours and drilled 914 mm (36”) hole from 524.5 to 572.5 mMDRT. Circulated clean and displaced hole to PHG mud. POOH. Rigged up and ran 762 mm (30”) conductor. Stabbed conductor into PGB below drill floor in moon pool. |
| --- | --- |
| NEXT 24 HOURS: | Complete cementing the 762 mm (30”) conductor. Release running tool and POOH. Lay down 914 mm (36”) BHA and cement head. RIH with 445 mm (17.5”) BHA and drill 445 mm (17.5”) hole. |
| MIDNIGHT TO 0600hrs SUMMARY: | Picked up PGB and confirmed engagement with conductor. Ran 762 mm (30”) conductor to 569.44 mMDRT. Commenced cementing the 762 mm (30”) conductor. |
| CURRENT OPERATION @ 06:00hrs: | Cementing 762 mm (30”) conductor. |

## GEOLOGICAL SUMMARY

LITHOLOGY

# Returns to seafloor.

HYDROCARBON FLUORESCENCE

Returns to seafloor.

# GAS SUMMARY

| Background | Total GAS (%) | C1 (%) | C2 (%) | C3 (%) | IC4 (%) | NC4 (%) | IC5 (%) | NC5 (%) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No returns | - | - | - | - | - | - | - | - |
| Peaks | Total GAS (%) | C1 (%) | C2 (%) | C3 (%) | iC4 (%) | NC4 (%) | IC5 (%) | NC5 (%) |
| N/A | - | - | - | - | - | - | - | - |
| Connection | Total GAS (%) | C1 (%) | C2 (%) | C3 (%) | IC4 (%) | NC4 (%) | IC5 (%) | NC5 (%) |
| N/A | - | - | - | - | - | - | - | - |
| Trip | Total GAS (%) | C1 (%) | C2 (%) | C3 (%) | IC4 (%) | NC4 (%) | IC5 (%) | NC5 (%) |
| N/A | - | - | - | - | - | - | - | - |

FORMATION PRESSURE ESTIMATION

| ITEM | REMARKS |
| --- | --- |
| Mud weight | N/A |
| Connection gas | N/A |
| Trip gas | N/A |
| Background gas | N/A |
| Dxc exponent | N/A |
| ROP | N/A |
| Ditch cuttings | N/A |
| Mud temperature out | N/A |
| MWD resistivity | N/A |
| Pore Pressure Estimate | 1.03 sg EMW (estimate from town) |

# SAMPLE QUALITY

No returns.

### MUDLOGGING EQUIPMENT/PERSONNEL

Personnel: 2x Data Engineers, 4x Mudloggers (sharing sample catching duties).

Equipment: All consumables checked and sufficient to complete well.  The calcimeter and gas chromatograph have been calibrated.

BHI have resolved ascii export issues.

### MWD/LWD

Personnel:  2x LWD Engineers

2x Directional Drillers

Equipment: Primary tool for the 444 mm (17-1/2”) section has been made up and racked back in the derrick. Tools for the 311 mm (12-1/4”) section have not yet arrived to the rig.

###### WIRELINE

Personnel: No crew onboard.

### WELLSITE GEOLOGISTS

David Hartney / Todd Teasdale

| FIELD REPORTED PROVISIONAL FORMATION TOPS |
| --- |
| Formation | Marker | Predicted Top (m) | Actual Top (m) | Diff. | Reason |
|  |  | MDRT | TVDSS | +/- | MDRT | TVDRT | TVDSS | (MD) |  |
| Seabed |  | 506.5 | 485 | 15 | 524.5 | 524.5 | 503.0 | +18 | Tagged seabed |
| Port Campbell Limestone |  | 749.5 | 728.0 | 30 |  |  |  |  |  |
| Gellibrand Marl |  | 1040.5 | 1019.0 | 30 |  |  |  |  |  |
| Base Miocene Marker |  | 1331.5 | 1310.0 | 40 |  |  |  |  |  |
| Narrawaturk Marl |  | 1603.5 | 1582.0 | 70 |  |  |  |  |  |
| Dilwyn Formation |  | 1658.5 | 1637.0 | 70 |  |  |  |  |  |
| Massacre Formation |  | 1708.5 | 1687.0 | 70 |  |  |  |  |  |
| Skull Creek Formation |  | 2105.5 | 2084.0 | 90 |  |  |  |  |  |
| Thylacine Member |  | 2832.5 | 2811.0 | 170 |  |  |  |  |  |
| Flaxman Formation |  | 2858.5 | 2837.0 | 180 |  |  |  |  |  |
| Waare Formation |  | 3154.5 | 3133.0 | 220 |  |  |  |  |  |
| Eumeralla Formation |  | 3276.5 | 3255.0 | 240 |  |  |  |  |  |
| TD |  | 3326.0 | 3304.4 | 240 |  |  |  |  |  |
| TD max |  | 3566.0 | 3544.5 |  |  |  |  |  |  |

Note: All depths LAT

CUTTINGS SAMPLING SUMMARY

| Depth Interval (mMDRT) | Sampling rate | Samples missed |
| --- | --- | --- |
| No returns |  |  |

MUD / MUD FILTRATE SAMPLES

| Depth (mMDRT) | Sample type |
| --- | --- |
| None |  |

ISOTUBE SAMPLES

| Depth (mMDRT) | Date | Time | TG% | Remarks |
| --- | --- | --- | --- | --- |
| None |  |  |  |  |

# DEPTH TABLE

|  | mMDRT unless otherwise stated | Precision of depth quoted | Remark |
| --- | --- | --- | --- |
| RTE | 21.5 m above LAT | 1dp |  |
| Mudline | 524.5 m | 1dp |  |
| Water Depth | 524.5 m | 1dp |  |
| 914 mm (36”) TD | 572.5 m | 1dp |  |
| 508 mm (20”) csg shoe | 569.44 m | 2dp |  |
| 445mm (17-1/2”) TD |  | 0dp |  |
| 340mm (13-3/8”) csg shoe |  | 0dp |  |
| 311mm (12-1/4”) TD |  | 0dp |  |