LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 13 | DFS: | 13 | DATE : | 29-10-9 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1378 | LAST DEPTH : | 1378 | 24 HR PROGRESS: |  | PTD : |  |
| TOTAL FUEL : | 5,100 | FUEL USAGE : | 1,600 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Picked up on Casing then install and hang Casing off in Bradenhead with 40 k tension |
| Next 24 Hrs Op | Cut off Casings tub –lay out same-lay out BOP-remove spools-install the "B" section and BOP |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 3 | 4RR |  | Drilling |  |  | Density | 1387 | S.G. |
| Size (mm) | 216 | 216 |  | Tripping | 4.5 |  | Viscosity | 51 | Sec |
| Make | Reed | Reed |  | Surveys |  |  | Water Loss | 7.5 | Cc |
| Type | HD219 | TD43 |  | Wireline logging |  |  | pH | 8.0 | Strip |
| IADC Code | 2-1-7 | 4-37 |  | Testing/tools |  |  | Filter Cake | 2 | 32 nd |
| Serial Number | AO8438 | W73458 |  | Circulate Sample |  |  | PV / YP | 17/ 27 | Cp/lb/100’ |
| Nozzles (32) | 14-14-14 | 14-14-14 |  | Casing | 12.5 |  | Gels | 5 / 7 | S/m |
| Depth in (m) | 1184 | 1366 |  | Cementing | 2.0 |  | Sand | 0.55 | % Vol |
| Depth out (m) | 1366 | 1378 |  | Surveys |  |  | Solids | 10.0 | % Vol |
| Total Metres | 182 | 12 |  | Circulate & Condition | 2.0 |  | Oil |  | % Vol |
| Hours | 40 | 2 |  | Rig Service/slip & cut |  |  | K+ | 10,500 | Mg/l |
| WOB (kg) | 9,000 | 7,000 |  | Rig down bop |  |  | Chlorides | 17,000 | Mg/l |
| RPM | 100 | 100 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | 8-8-WT –A-E-1/8-ER-PR | 5-4-RG-H-E-1/8-ER-TD |  | Reaming |  |  | KCL | 2.0 | % |
| Impact Force | 415 |  |  | Wait On Cement | 3.0 |  | Daily Cost $ | 358 |
| Jet Velocity | 234 |  |  | Test BOPs |  |  | Cum Cost $ | 30,357 |
| B.H.A.: | BHA # 3 216mm Bit –Bit Sub-NMDC-1 x 6¼" DC-8½"Stab-7 x 6¼" Drill Collars-Drilling Jar-3 x 6¼"Drill Collars-4 x HWDP-Crossover sub |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 1½º N60E | ° at | 1354 | m |  | Type | Amount |
| 0000 | 04.30 | Layed out BHA –Stab-Jar –NMDC-and 216mm Bit |  |  | ° at |  | m |  |  |  |
| 04.30 | 07.00 | Rigged up for Casing changed out Rams to 7" |  |  | ° at |  | m |  |  |  |
| 07.00 | 17.00 | Ran 117 jnts of 36ppf K-55 BTC Casing to 1370m |  |  | ° at |  | m |  |  |  |
| 17.00 | 17.30 | Circulated and washed down to 1376m |  |  | ° at |  | m |  | Barite Lakes | 86 |
| 17.30 | 19.00 | Circulated –Held safety meeting –tested lines |  |  | ° at |  | m |  | Potassium Chloride | 9 |
| 19.00 | 21.00 | Cemented casing –displaced bumped plug 2,500psi |  |  | ° at |  | m |  |  |  |
| 21.00 | 24.00 | Plug held good –bled off –WOC-prepare to pick up |  |  | ° at |  | m |  |  |  |
|  |  | and hang off the BOP |  |  |  |  |
|  |  |  |  | PUMP 1 Duplex |  | PUMP 2 Triplex |
|  |  | Down hole losses in formation while cementing and |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  | displacing ( probably in coal sections ) |  | Pressure |  | kPa |  | Pressure |  | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP |  | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC |  | m/min |
|  |  | 1 Load of water |  | SPM |  |  | SPM |  |
|  |  |  |  | LPM |  |  | LPM |  |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 7" | inch |
|  |  |  |  | Class Bulk |  |  | Weight | 26 | ppf |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Connection | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 117 |  |
|  |  |  |  | % |  |  |  | Length | RT-Brd Hd 5.0 | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 1376m from RKB | m |

,66