LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 17 | DFS: | 17 | DATE : | 2-11-09 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1,478 | LAST DEPTH : | 1,478 | 24 HR PROGRESS: |  | PTD : |  |
| TOTAL FUEL : | 6,000 | FUEL USAGE : | 1,200 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Break out DST tools at surface Recovered mud only when reversed out |
| Next 24 Hrs Op | Lay out DST tools-Trip in hole and Drill ahead with 156mm bit |
| Site Personnel: | Lou DeVattimo - Supervisor |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 5 |  |  | Drilling |  |  | Density | 1.176 | S.G. |
| Size (mm) | 156 |  |  | Tripping |  |  | Viscosity | 46 | Sec |
| Make | Smith |  |  | Surveys |  |  | Water Loss |  | Cc |
| Type | MDi613 |  |  | Wireline logging |  |  | pH | 9.5 | Strip |
| IADC Code |  |  |  | Testing/tools | 24 |  | Filter Cake | 2 | 32 nd |
| Serial Number | JD1042 |  |  | Circulate Sample |  |  | PV / YP | 15/ 25 | Cp/lb/100’ |
| Nozzles (32) | 3 x 12 |  |  | Casing |  |  | Gels | 5 / 7 | S/m |
| Depth in (m) | 1378 |  |  | Cementing |  |  | Sand | 0.40 | % Vol |
| Depth out (m) | 1478 |  |  | Surveys |  |  | Solids | 9.5 | % Vol |
| Total Metres | 100 |  |  | Circulate & Condition |  |  | Oil |  | % Vol |
| Hours | 7.5 |  |  | Rig Service/slip & cut |  |  | K+ |  | Mg/l |
| WOB (kg) | 2,000 |  |  | Rig up/ d own bop |  |  | Chlorides | 18,000 | Mg/l |
| RPM | 100 |  |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | AS NEW |  |  | Reaming |  |  | KCL | 2.0 | % |
| Impact Force | 257 |  |  | Wait On Cement |  |  | Daily Cost $ | 0 |
| Jet Velocity | 219 |  |  | Test BOPs |  |  | Cum Cost $ | 55,151 |
| B.H.A.: 5 | DST Tools Run # 1 |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | 1½º N60E | ° at | 1354 | m |  | Type | Amount |
| 0000 | 02.00 | Tripped out with DST tool –repaired the fault i n tool |  |  | ° at |  | m |  | AMC Biocide G |  |
| 02.00 | 06.00 | Tripped in hole with DST tools |  |  | ° at |  | m |  | Sodium sulphite |  |
| 06.00 | 08.00 | Rigged up surface testing equipment –tested lines |  |  | ° at |  | m |  | Barytes |  |
| 08.00 | 09.00 | Held safety meeting then made some attempts to set the |  |  | ° at |  | m |  |  |  |
|  |  | Packer inside Casing , slipped |  |  | ° at |  | m |  |  |  |
| 09.00 | 10.00 | Picked up one single set packer in open hole 1,383m |  |  | ° at |  | m |  | Residrill |  |
| 10.00 | 12.00 | Set Packer opened tool for 15mins-shut in for 90mins |  |  | ° at |  | m |  |  |  |
| 12.00 | 15.30 | Open tool monitored well |  |  |  |  |
| 15.30 | 24.00 | Closed tool |  | PUMP 1 Duplex |  | PUMP 2 Triplex |
|  |  |  |  | Liner | 140 | mm |  | Liner | 140 | mm |
|  |  |  |  | Pressure |  | kPa |  | Pressure | 7,700 | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP | 220 | Ft/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC | 371 | Ft//mn |
|  |  | Very small flow of Gas at initial flow –no condensate |  | SPM |  |  | SPM | 100 |
|  |  |  |  | LPM |  |  | GPM | 227 |
|  |  | Held weekly safety meeting |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton |  |  | Size | 7" | inch |
|  |  | Hunt 18 Camp 4 |  | Class Bulk |  |  | Weight | 26 | ppf |
|  |  | Lakes 4 |  | % |  |  |  | Grade | K-55 |  |
|  |  | Mud logger 2 |  | % |  |  |  | Connection | BTC |  |
|  |  | Farley Riggs 4 |  | % |  |  |  | Joints | 117 |  |
|  |  | RMN 1 |  | % |  |  |  | Length | RT-Brd Hd 5.0 | m |
| Days since | LTA |  |  | Av. Wt |  |  | Shoe | 1376m from RKB | m |

,66