LAKES OIL N.L

DAILY DRILLING REPORT

| WELL : | Wombat-4 | REPORT No. : | 8 | DFS: | 8 | DATE : | 24-10-09 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2400 DEPTH : | 1120m | LAST DEPTH : | 958m | 24 HR PROGRESS: | 162m | PTD : |  |
| TOTAL FUEL : | 7,750 | FUEL USAGE : | 2,100 | DAYCOST : $ |  | CUM. COST : $ |  |
| 0600 OPS : | Drilling 216mm hole at 1164m |
| Next 24 Hrs Op | Drill ahead to 7" casing depth |
| Site Personnel: | Hunt Energy 21 Camp 4 Lakes Oil 4 RMN 1 Baker Mud Loggers 2 |

| BIT INFORMATION |  | OPS BREAKDOWN |  | MUD PROPERTIES |
| --- | --- | --- | --- | --- |
| Bit Number | 1 Re-run | 2 |  | Drilling | 14.5 |  | Density | 1.126 | S.G. |
| Size (mm) | 311 | 216 |  | Tripping |  |  | Viscosity | 47 | Sec |
| Make | Reed | Reed |  | Slip Cut |  |  | Water Loss | 8.0 | Cc |
| Type | EPH41 HKPR | RO1APDH |  | BHA |  |  | pH | 8.5 | Strip |
| IADC Code | 4-1-7 | 4-1-7 |  | F.I.T |  |  | Filter Cake | 1.0 | 32 nd |
| Serial Number | NR 2008 | NDO593 |  | Circulate Sample |  |  | PV / YP | 16 / 23 | Cp/lb/100’ |
| Nozzles (32) | 18-18-18 | 14-14-14 |  | Casing |  |  | Gels | 4 / 6 | S/m |
| Depth in (m) | 16 | 302 |  | Cementing |  |  | Sand | 0.35 | % Vol |
| Depth out (m) | 302 |  |  | Surveys | 0.5 |  | Solids | 8.8 | % Vol |
| Total Metres | 285 / 846 | 818 |  | Circulate & Condition | 1.0 |  | Oil |  | % Vol |
| Hours | 18.5 / 63.5 | 69.5 |  | Rig Service | 0.5 |  | K+ | 11,550 | Mg/l |
| WOB (kg) | 2000 | 4000 / 5000 |  | Rig up/down bop |  |  | Chlorides | 20,000 | Mg/l |
| RPM | 100 | 100 |  | Drill out Cmt |  |  | PHPA |  |  |
| Condition | 2-2-NO-A-E-1-1-CT | S.I.H |  | Wiper trip | 7.5 |  | KCL | 2.2 | % |
| Impact Force |  | 352 |  | Wait On Cement |  |  | Daily Cost $ | 4,203 |
| Jet Velocity |  | 223 |  | Test BOPs |  |  | Cum Cost $ | 24,260 |
| B.H.A.: # 2 | 216mmBit-NBS-NMDC-Stab- 2 x 6¼" DC-Stab-6 x 6¼" DC-Supra Drilling Jar- 3 x 6¼" DC-4 x HWDP- X/O Sub Length 162.44m |
|  | Total drill pipe on site 118 in hole 99 Total 217 |
| HOURLY OPERATIONS SUMMARY (0000 – 2400) |  | SURVEYS |  | CHEMICALS USED |
| From | To | Operation |  | ¾º | ° at | 32 | m |  | Type | Amount |
| 00.00 | 07.30 | Drilled 216mm hole from 958m to 1053m |  | ½º | ° at | 96 | m |  | AMC Pac R | 6 |
| 07.30 | 08.00 | Serviced the rig |  | 1º | ° at | 239 | m |  | Caustic | 1 |
| 08.00 | 11.30 | Drilled 216mm hole from 1053m to 1092m |  | 1½º | ° at | 295 | m |  | KCL | 40 |
| 11.30 | 12.00 | Circulated hole clean pumped pill |  | N25deg E2 | ° at | 458 | m |  | Xan Bore | 4 |
| 12.00 | 15.30 | Wiper tripped hole back to 745m max overpull 15klbs |  | N 86deg E 2 | ° at | 687 | m |  | Barite (Lakes) | 255 |
|  |  | from 984m to 879m |  | N 50deg E 3 | ° at | 917 | m |  |  |  |
| 15.30 | 16.30 | Tripped back in hole to 1032m ( resistance ) |  | N88d E 3 | ° at | 1079 | m |  |  |  |
| 16.30 | 19.30 | Picked up Kelly cleaned hole to bottom at 1092m |  |  |  |  |
| 19.30 | 20.00 | Circulated hole clean |  | PUMP 1 |  | PUMP 2 |
| 20.00 | 20.30 | Ran survey at 1079m |  | Liner | 140 | mm |  | Liner | 140 | mm |
| 20.30 | 24.00 | Drilled 216mm hole from 1092m to 1120m |  | Pressure |  | kPa |  | Pressure | 7,300 | KPa |
|  |  |  |  | A.V. DP |  | m/min |  | A.V. DP | 40 | m/min |
|  |  |  |  | A.V. DC |  | m/min |  | A.V. DC | 70 | m/min |
|  |  |  |  | SPM |  |  | SPM | 140 |
|  |  |  |  | LPM |  |  | LPM / GPM | 1230 / 325 |
|  |  |  |  | CEMENT DATA |  | LAST CASING |
|  |  |  |  | Sacks Halliburton | 377 |  | Size | 9⅝" | inch |
|  |  |  |  | Class Bulk |  |  | Weight | 36 | ppf |
|  |  |  |  | % |  |  |  | Grade | K-55 |  |
|  |  |  |  | % |  |  |  | Thread | BTC |  |
|  |  |  |  | % |  |  |  | Joints | 25 |  |
|  |  |  |  | % |  |  |  | Length |  | m |
| Days since | LTA |  |  | Av. Wt | 15.6 |  | Shoe | 299.00 | m |

,66